## Estimate
Superior Beverage Exotec |  |  | 2026-03-13
The Alleato Group . 8383 Craig St #150 . Indianapolis, IN . 46250
Contact | Brandon Clymer | bclymer@alleatogroup.com | 317-760-0088
Project: | Superior Beverage Exotec
Location: | Glenwillow, OH
RFP ITEMS
#1 | General Conditions, Supervision |  | 178920
#2 | Furnsih and install Sprinkler System for Exotec |  | 1016918 | 0 | 1016918
#3 | Sprinkler Design |  | 145000 |  | 145000
| Contingency |  | 0
| Insurance |  | 16761
|  | Fee | 135760
| RFP TOTAL |  | 1493359 |  |  | 1407956 | 8 wk duration
[6 empty] | 1507593 | 15 wk duration
Alternates
1
[6 empty] | 1578761 | 20 wk duration
170805

## Material Take Off
[5 empty] | Labor |  |  | Equipment
Material | 313168 |  |  |  | Hours | Rate |  | Duration | Rate
Labor | 603750 |  |  |  | 4025 | 150 | 603750 | 14 | 2000 | 28000
Equipment
Contingency | 100000
Total | 1016918 | [10 empty] | Fabrication | Loose | Total
[11 empty] | Legacy (Heads) |  |  | 0
[11 empty] | Core and Main | 21974.63 |  | 21974.63
|  |  |  | 3515 | PM | 49210 |  |  |  |  | Ferguson | 17873.65 | 17084.53 | 34958.18
|  |  |  | 3515 | Super | 49210
|  |  |  | 5000 | Travel | 70000 | [5 empty] | Base | Bulk Main | Total
Material | Qty |  |  | 750 | Truck | 10500 | [7 empty] | 0
Heads | 7184 | ea | 14.5 | 104168 | [9 empty] | 0
2" Fab Pipe | 4256 | lf |  | 209000
2" Caps | 28 | ea |  |  |  | 178920
Glue | 2 | ea
Hangers | 392 | ea
2" Couplings | 28 | ea
3" Bulk | 350 | lf
Riser | 1 | lot
3" Couplings | 20 | ea
3" - 2" M-Ts | 28 | ea
2" 90s | 0 | ea
3" caps | 14 | ea
6" bulk | 550 | lf
6" 90s | 4
6" end cap | 1
6" Couplings | 27.5
2" Slick Pipe | 1631 | lf
Viking | Tyco | Reliable | Victaulic | Globe | Senju
VK300 | TY7151 | F1FR56 | V27 | GL-QR 112 | S3VK11
VK302 | TY5151 | F1FR42 |  | GL-QR 112