## Sheet1
Report Type: Punch List
Project: 24-115 Westfield Collective
Status | Priority | Item Number | Title | Assigned To | Due Date | Category | Location
Assigned | Low | 019 | 2nd floor beer wall | Alleato Group | 02/25/2026 |  | 2nd floor beer wall
Assigned | Medium | 102 | Install vapor barrier in woman's restroom | Alleato Group | 02/13/2026
Assigned | Medium | 103 | Install insulation in woman's and men's restroom | Alleato Group | 02/11/2026 |  | volleyball men's and woman's restroom
Assigned | Medium | 128 | Hole In The Wall (Spectrum) | Alleato Group |  | Owner | 2nd Floor South West Wall
Assigned | Low | 142 | Cap Ends On Roll Up Doors | Alleato Group |  |  | 2nd Story West Dining
Assigned | Low | 146 | Spectrum Hole | Alleato Group
Assigned | Low | 161 | Aluminum On Threash Hold | Alleato Group | 02/12/2026 |  | East Dining
Assigned | High | 165 | Install Elevator Flooring | Alleato Group | 02/13/2026 |  | Elevator
Assigned | Medium | 169 | Spectrum Wire (Mike) | Alleato Group | 02/11/2026 |  | 2nd Floor West Patio
Assigned | Medium | 192 | AV Boxes Incomplete | Alleato Group | 02/13/2026 |  | Exposed 2nd Floor Patio
Assigned | Medium | 195 | Cap Anchor Bolts | Alleato Group | 02/12/2026 |  | Down Stairs Porch
Assigned | Medium | 046 | Casework | Casework Concepts LLC | 02/10/2026 |  | 2nd floor West Dining Area
Assigned | Medium | 048 | Casework and electrical hookup | Casework Concepts LLC | 02/13/2026 |  | Beer wall/ Common area
Assigned | Low | 054 | Install toe kicks | Casework Concepts LLC | 02/06/2026 |  | Beer wall/ Common area
Assigned | Medium | 065 | Finish casework | Casework Concepts LLC | 02/13/2026 |  | Dining area
Assigned | Medium | 068 | Case work | Casework Concepts LLC | 02/11/2026 |  | Family Room
Assigned | Medium | 083 | Finish casework and trim | Casework Concepts LLC | 02/10/2026 |  | hostess stand
Assigned | Medium | 088 | Case work | Casework Concepts LLC | 02/10/2026 |  | 2nd floor East Dining Area
Assigned | Low | 127 | Toe Kick Missing | Casework Concepts LLC |  |  | West 2nd Floor Dining
Assigned | High | 130 | Wood Shelf’s | Casework Concepts LLC | 02/11/2026 | Casework | Next To Second Floor Pvt Room
Assigned | Medium | 150 | Complete Casework 2nd Floor North Seating | Casework Concepts LLC | 02/12/2026 |  | North Second Floor
Assigned | Low | 155 | East Dining Area Adhesive Brackets | Casework Concepts LLC |  |  | East Dining
Assigned | Medium | 157 | Replicate Other Case Work In This Area | Casework Concepts LLC | 02/13/2026 |  | East Dining
Assigned | Medium | 157 | Replicate Other Case Work In This Area | Casework Concepts LLC | 02/13/2026 |  | East Dining
Assigned | Medium | 159 | Replicate Other Case Work In This Area | Casework Concepts LLC | 02/13/2026 |  | East Dining
Assigned | High | 162 | Add Adhesive For Shelf’s | Casework Concepts LLC |  |  | All Shelf Locations
Assigned | Medium | 168 | Complete 2nd Floor Landing Casework By Fireplace Wall | Casework Concepts LLC | 02/11/2026
Assigned | Medium | 100 | Finish caulking on doors | Caulking Specialists | 02/10/2026 |  | VB
Assigned | Low | 109 | Finishing caulking the top of the tile | Caulking Specialists | 02/11/2026 |  | volleyball men's and woman's restroom
Assigned | Medium | 112 | Exact same as A | Caulking Specialists | 02/12/2026 |  | vendor B
Assigned | Medium | 113 | Same as A | Caulking Specialists | 02/12/2026 |  | Vendor C
Assigned | Medium | 114 | Exact same as A | Caulking Specialists | 02/12/2026 |  | Vendor D
Assigned | Medium | 115 | exact as vendor A | Caulking Specialists | 02/12/2026 |  | vendor E
Assigned | Low | 137 |  | Caulking Specialists |  |  | 2 Floor Dining West
Assigned | Low | 145 | Caulk Bottom Of Tile | Caulking Specialists | 02/12/2026 |  | 2nd Floor Dining
Assigned | Low | 153 | Caulk Around All Door Jambs | Caulking Specialists
Assigned | Medium | 170 | West Side Porch Caulking | Caulking Specialists | 02/13/2026 |  | West Side Porch
Assigned | Medium | 022 | Patch Electrical holes | Deem, LLC | 02/06/2026 |  | 2nd floor beer wall
Assigned | Medium | 026 | Fire alarm devices | Deem, LLC | 02/09/2026 |  | 2nd floor beer wall
Assigned | Medium | 033 | 2nd floor bar rope lighting | Deem, LLC | 02/10/2026 |  | 2nd floor bar
Assigned | Medium | 039 | Conduit on North wall | Deem, LLC | 02/10/2026 |  | 2nd floor bar
Assigned | Medium | 055 | Switch device | Deem, LLC | 02/10/2026 |  | Private Room
Assigned | Medium | 072 | Bar lighting | Deem, LLC | 02/11/2026 |  | 1st floor bar
Assigned | Medium | 085 | Fire Caulk | Deem, LLC | 02/09/2026 |  | Storage 210
Assigned | Medium | 108 | Remove light switch | Deem, LLC | 02/06/2026 |  | volleyball men's and woman's restroom
Assigned | Low | 129 | 2nd Floor West Dining | Deem, LLC |  |  | 2nd Floor West Dining
Assigned | Low | 131 | Light Install | Deem, LLC | 02/10/2026 |  | 2nd Floor West Dining
Assigned | Low | 132 | Remove Bags From Lights | Deem, LLC | 02/10/2026 |  | 2 Floor Dining West
Assigned | Low | 136 | Covers On Junction Boxes | Deem, LLC |  |  | Upstairs 2nd Dining
Assigned | Low | 138 | Drywall Square Repair | Deem, LLC | 02/13/2026 |  | 2nd Floor West Dining
Assigned | Medium | 167 | Install Fireplace | Deem, LLC | 02/12/2026 |  | 2nd Floor Landing
Assigned | Medium | 171 | Outlet 2nd Floor South Patio | Deem, LLC | 02/11/2026
Assigned | Medium | 172 | West Side Porch Grind Off Screws | Deem, LLC | 02/13/2026 |  | West Side Porch
Assigned | Medium | 173 | West Side Porch Grind Off Screws | Deem, LLC | 02/13/2026 |  | West Side Porch
Assigned | High | 174 | Rough In For Lights Men’s 1st And 2nd Floor Bathrooms | Deem, LLC | 02/10/2026 |  | 2nd Floor Men’s And Women’s Bathrooms
Assigned | Medium | 178 | Remove All Unused Conduits On 2nd Floor Patio | Deem, LLC | 02/13/2026 |  | 2nd Floor Patio
Assigned | Medium | 180 | Electrical Box 2nd Floor Patio | Deem, LLC | 02/10/2026 |  | 2nd Floor Patio
Assigned | Medium | 182 | Outlet Second Floor Patio | Deem, LLC | 02/13/2026 |  | North Second Level Patio
Assigned | Medium | 183 | Address Fire Device | Deem, LLC | 02/12/2026 |  | North Side Porch
Assigned | Medium | 184 | North Side Porch Device | Deem, LLC | 02/13/2026 |  | North Side Porch
Assigned | High | 185 | FA Device North 2nd Floor Patio | Deem, LLC | 02/10/2026
Assigned | High | 191 | Missing FA device | Deem, LLC | 02/13/2026
Assigned | Medium | 196 | Address Junction Boxes | Deem, LLC |  |  | Coffee Bar
Assigned | Medium | 197 | Electrical Wip’s | Deem, LLC | 02/12/2026
Assigned | Medium | 198 | Electrical Wip’s | Deem, LLC | 02/12/2026
Assigned | Medium | 181 | Paint Touch Up Around Window | EURO Plastering |  |  | North Side Window
Assigned | Medium | 002 | Elevator Install | Executive Elevator Company | 02/06/2026
Assigned | Medium | 099 | Finish elevator room | Executive Elevator Company | 02/11/2026 |  | elevator room
Assigned | Medium | 034 | 2nd floor bar equipment | FG Schaefer Co | 02/13/2026 |  | 2nd floor bar
Assigned | Medium | 071 | Bar equipment install hook up | FG Schaefer Co | 02/11/2026 |  | 1st floor bar
Assigned | Medium | 078 | equipment install in creamery area | FG Schaefer Co | 02/13/2026 |  | creamery area
Assigned | Low | 111 | Equip hook up | FG Schaefer Co | 02/12/2026 |  | vendor A
Assigned | Medium | 030 | Mop sink install | Justin Dorsey Plumbing | 02/09/2026 |  | Commisarry area
Assigned | Medium | 081 | Creamery equip install hook up | Justin Dorsey Plumbing | 02/13/2026 |  | Creamery area
Assigned | Medium | 107 | Finish Plumbing | Justin Dorsey Plumbing | 02/11/2026 |  | volleyball men's and woman's restrooms
Assigned | Low | 110 | Caulk floor drain | Justin Dorsey Plumbing | 02/06/2026 |  | vendor A
Assigned | Low | 121 | Calk Drains | Justin Dorsey Plumbing | 02/16/2026 |  | Woman’s RR
Assigned | Low | 134 | Plumbers Tape Around Gas Pipe | Justin Dorsey Plumbing |  |  | 2nd Story West Dining
Assigned | High | 144 | Core For Pepsi Line | Justin Dorsey Plumbing | 02/12/2026 |  | 2nd Floor Bar
Assigned | Low | 151 | Clean Tile From Concrete Slurry | Justin Dorsey Plumbing |  |  | Men’s And Women’s 2nd Floor Bathrooms
Assigned | High | 147 | Tape Coming Off Ceiling Insulation | Lemaster Steel Erectors Inc. | 02/12/2026 |  | 2nd Floor North Seating
Assigned | Medium | 189 | Silicone Gutter | Lemaster Steel Erectors Inc. | 02/12/2026 |  | East Side Porch
Assigned | Medium | 186 | Secure Post | LeMaster Steel Erectors Inc. | 02/12/2026 |  | North Side
Assigned | Medium | 187 | Secure Post | LeMaster Steel Erectors Inc. | 02/12/2026 |  | North Side
Assigned | Medium | 094 | Install back counter top | Marble Uniques | 02/12/2026 |  | Bourban bar
Assigned | Low | 106 | Finish countertops in bathrooms | Marble Uniques |  |  | men and woman's volleyball bathrooms
Assigned | Low | 143 | Counter Top Polish | Marble Uniques | 02/12/2026 |  | 2nd Floor
Assigned | Medium | 179 | Polish Counter Edge | Marble Uniques |  |  | North Side Porch
Assigned | High | 200 | Countertop Install (First Floor Trash unit) | Marble Uniques | 02/13/2026 |  | First Floor North West Seating
Assigned | Medium | 027 | Install cove base. | Market Ready Interiors Inc | 02/10/2026 |  | Commisarry area
Assigned | Medium | 038 | Install cove base. | Market Ready Interiors Inc | 02/09/2026 |  | Commisarry Hall
Assigned | Medium | 045 | Finish Tile | Market Ready Interiors Inc | 02/13/2026 |  | Beer Wall common area
Assigned | Medium | 049 | Cove base | Market Ready Interiors Inc | 02/10/2026 |  | 2nd floor West Dining Area
Assigned | Medium | 061 | Finish cove base installation | Market Ready Interiors Inc | 02/06/2026 |  | Dining area
Assigned | Medium | 073 | Finish tile | Market Ready Interiors Inc | 02/13/2026 |  | Creamery
Assigned | Low | 080 | Cove base | Market Ready Interiors Inc | 02/10/2026 |  | POD cast room
Assigned | Medium | 091 | Install cove base | Market Ready Interiors Inc | 02/06/2026 |  | hostess stand area
Assigned | Medium | 092 | Finish SSB | Market Ready Interiors Inc | 02/06/2026 |  | Bourban bar
Assigned | Low | 097 | Finish installing cove base | Market Ready Interiors Inc | 02/06/2026 |  | Bourban bar
Assigned | Low | 152 | Clean Off Grout | Market Ready Interiors Inc | 02/13/2026 |  | Men’s Bathroom
Assigned | High | 156 | Schluter Strip Not To The Finish Level Of Tile. Stopped Short | Market Ready Interiors Inc | 02/11/2026
Assigned | Low | 160 | Market Ready Base Trim | Market Ready Interiors Inc | 02/12/2026 |  | East Dining
Assigned | Medium | 199 | Base Board On Creamery | Market Ready Interiors Inc | 02/12/2026 |  | Creamery
Not Resolved | Medium | 008 | Touch up paint | S&M Painting | 02/10/2026 |  | 2nd floor men's restroom
Assigned | Low | 015 | Touch up paint | S&M Painting | 02/12/2026 |  | 2nd floor women's restroom
Assigned | Medium | 037 | Touch up SSB | S&M Painting | 02/11/2026 |  | 2nd floor bar
Assigned | Medium | 041 | Touch up paint at 2nd floor bar | S&M Painting | 02/10/2026 |  | 2nd floor bar
Assigned | Low | 042 | Touch up paint spots in commissary area | S&M Painting | 02/10/2026 |  | Commisarry area
Assigned | Medium | 053 | Touch up paint | S&M Painting | 02/11/2026 |  | 2nd floor West Dining Area
Assigned | Medium | 056 | Touch up SSB | S&M Painting | 02/13/2026 |  | Beer wall/ Common area
Assigned | Medium | 060 | Touch up | S&M Painting | 02/11/2026 |  | Private Room
Assigned | Medium | 066 | Touch up | S&M Painting | 02/12/2026 |  | Family Room
Assigned | Medium | 070 | Touch up paint on ssb | S&M Painting | 02/12/2026 |  | 1st floor bar
Assigned | Medium | 079 | Touch up | S&M Painting | 02/06/2026 |  | POD cast room
Assigned | Medium | 086 | SSB touch up | S&M Painting | 02/06/2026 |  | hostess stand area
Assigned | Medium | 087 | Touch up | S&M Painting | 02/11/2026 |  | Storage 210
Assigned | Medium | 096 | Finis touch up paint at bourbon bar. | S&M Painting | 02/06/2026 |  | Bourban bar
Assigned | Low | 125 | Pain Touch Up | S&M Painting |  | Punch
Assigned | Low | 139 | Paint Sprinkler Pipes | S&M Painting
Assigned | Low | 140 | Paint Black Pipe | S&M Painting | 02/18/2026 |  | 2nd Story Dining
Assigned | Medium | 176 | Paint Beam | S&M Painting | 03/05/2026 |  | West
Not Resolved | Low | 003 | Drywall Touch up | Superior Contractors | 02/06/2026 |  | 2nd floor men's restroom
Assigned | Medium | 016 | Bathroom accessories | Superior Contractors | 02/12/2026 |  | 2nd floor women's restroom
Assigned | Low | 018 | Drywall touch up | Superior Contractors | 02/10/2026 |  | 2nd floor beer wall
Assigned | Medium | 043 | Drywall touch up | Superior Contractors | 02/10/2026 |  | 2nd floor West Dining Area
Assigned | Low | 069 | Drywall patch and paint | Superior Contractors | 02/11/2026 |  | 1st floor bar
Assigned | Medium | 101 | Finish drywall touch up and paint | Superior Contractors | 02/06/2026 |  | VB
Assigned | Medium | 104 | Finish ACT pad installation | Superior Contractors | 02/11/2026 |  | volleyball men's and woman's restrooms
Assigned | Medium | 105 | Finish partitions in RR volleyball area | Superior Contractors | 02/12/2026 |  | volleyball men's and woman's restrooms
Assigned | Low | 118 | Act Tiles | Superior Contractors | 02/09/2026 |  | Mens Bathroom
Assigned | Low | 123 | Partitions Install | Superior Contractors |  |  | Woman’s RR
Assigned | Low | 133 | Drywall Hole | Superior Contractors | 02/13/2026 |  | 2nd Floor Dining West
Assigned | Low | 148 | Drywall | Superior Contractors |  |  | 2nd Floor Beer Wall
Assigned | Low | 166 | Repair Drywall | Superior Contractors | 02/12/2026 |  | West Side Dining
Assigned | Medium | 188 | Install 1xs | Superior Contractors | 02/12/2026 |  | East Side Porch
Assigned | Low | 120 | Act Tiles | Superior Contractors Inc | 02/09/2026 |  | Woman’s RR
Assigned | Medium | 135 | Drywall Over PEMB Support | Superior Contractors Inc | 02/18/2026 | Drywall Touch Up | 2nd Floor West Wall
Assigned | Medium | 141 | Adjust 2nd Floor Bar Counter Supports (not Level) | Superior Contractors Inc |  |  | 2nd Floor Bar
Assigned | Low | 149 | Repair Drywall | Superior Contractors Inc | 02/13/2026 |  | 2nd Floor Beer Wall
Assigned | Low | 154 | Sand Drywall. East Dining Hall | Superior Contractors Inc |  |  | East Dining Hall
Assigned | Medium | 163 | Replace Broken Kebony Board | Superior Contractors Inc | 02/11/2026 |  | West Exterior Staircase
Assigned | Medium | 164 | Complete South Patio Kebony Rail | Superior Contractors Inc |  |  | South End Of 2nd Floor Patio
Assigned | Medium | 190 | Straighten Wood Patio Rail and install back cap | Superior Contractors Inc | 02/12/2026 |  | Exposed Patio (north Second Floor)
Assigned | Medium | 193 | Complete Kebony Wood Handrail | Superior Contractors Inc | 02/14/2026 |  | North Exterior Staircase
Assigned | Medium | 194 | Complete West Staircase Kebony Board | Superior Contractors Inc | 02/10/2026 |  | 2nd floor West Patio
Assigned | Medium | 201 | Drywal finish elevator openings 1st and 2nd floor | Superior Contractors Inc | 02/13/2026
Assigned | Low | 202 | Sand drywall at 1st and 2nd floor bar | Superior Contractors Inc | 02/16/2026
Assigned | Medium | 203 | Fix drywall outside of volleyball bathrooms | Superior Contractors Inc
Assigned | Medium | 047 | Data | Tri-State AV | 02/11/2026 |  | 2nd floor West Dining Area
Assigned | Medium | 059 | Finish out data | Tri-State AV | 02/13/2026 |  | Dining area
Assigned | Medium | 014 | Replace ACT tile | Vulcn | 02/18/2026 | L2 zone 1 | 2nd floor women's restroom