## Sheet1
Report Type: Change Request |  |  | Funds moved to GC or Design |  |  |  |  | Sub CO not issued |  | Contingency
Project: 24-115 Westfield Collective |  |  | Owner CO Not Written |  |  |  |  | Sub CO Issued
|  |  | Owner CO Written, Fee/Ins broke out |  |  |  |  | Internal CO Loss
Title Number | Contract | Scope | Status | Sub | Status | Cost | Mark Up | Fee | Insurance | Total | Over/Under
CR-2403-0002 Secondary Plat Services | PC-2403-0001 | Owner Change | Approved |  |  | 3500 |  | 354.38 | 43.75 | 3898.13 | 398.13
CR-2403-0003 Permits and Inspections | PC-2403-0001 | Owner Change | Approved |  |  | 37896.76 |  | 3837.04 | 473.71 | 42207.51 | 4310.75
CR-2403-0004 Vacation and Reconstruction of Existing Drain Tile | PC-2403-0001 | Owner Change | Approved |  |  | 15722.93 | 0 | 1591.95 | 196.54 | 17511.42 | 1788.49
CR-2403-0005 Removal of Additional Concrete Foundations | PC-2403-0001 | Internal | Approved |  |  | 3889.25 | 0 | 0 | 0 | 0 | -3889.25
CR-2403-0006 ROW Scope Increase From City | PC-2403-0001 | Owner Change | Approved | Howard | included in subcontract amount | 10856 | 10000 | 2111.67 | 260.7 | 23228.37 | 12372.37
CR-2403-0007 Site Work Adds From City Review | PC-2403-0001 | Owner Change | Approved | United | included in subcontract amount | 15349 | 6000 | 2161.59 | 266.87 | 23777.46 | 8428.46
CR-2403-0008 Add Kitchen Design and Buildout | PC-2403-0001 | Owner Change | Approved |  |  | 286665 | 16700 | 30715.71 | 3792.07 | 337872.78 | 51207.78
CR-2403-0010 Deduct To Split Buildings | PC-2403-0001 | Owner Change | Approved
CR-2403-0012 Add Structure 612 | PC-2403-0001 | Internal | Approved |  |  | 3932.08 | 0 | 0 | 0 | 0 | -3932.08
CR-2403-0015 United Excavating T&M Tickets | PC-2403-0001 | Pricing in CR #04 & #05 | Approved | [5 empty] | 0 | 0 | 0
CR-2403-0016 Elevator Equipment Room Relocation | PC-2403-0001 | Internal | Approved |  |  | 2260 | 0 | 0 | 0 | 0 | -2260
CR-2403-0018 Damn Good Interiors Design | PC-2403-0001 | Owner Change | Approved |  |  | -16068 | 8032 | 0 | 0 | -8036 | -8036
CR-2403-0019 Center Point Energy Encroachment Application | PC-2403-0001 | Owner Change | Approved |  |  | 1300 | 0 | 131.63 | 16.25 | 1447.88 | 147.88
CR-2403-0020 IBeach Logistics Adds | PC-2403-0004 | Owner Change | Approved |  |  | 2378 | 0 | 240.78 | 29.73 | 2648.51 | 270.51
CR-2403-0021 Trail Pavement Section Credit | PC-2403-0001 | Internal | Approved |  |  | -3321.25 | 0 | 0 | 0 | -3321.25 | 0
CR-2403-0023 Additional Surveying | PC-2403-0001 | Owner Change | Approved |  |  | 1650 | 850 | 253.13 | 31.25 | 2784.38 | 1134.38
CR-2403-0024 Lime Stabilization | PC-2403-0001 | OCO PC #47 | Void |  |  | 80437.5 | -80437.5 | 0 | 0 | 0 | 0
CR-2403-0025 R15 ISO at Foundation Perimeter | PC-2403-0001 | OCO PC #47 | Void |  |  | 4304.37 | 0 | 0 | 0 | 4304.37 | 4304.37
CR-2403-0026 Items in PCCO 20 Paint Structural Steel | PC-2403-0001 | Owner Change | Approved |  |  | 15000 | 531.25 | 0 | 0 | 0 | 0
CR-2403-0026 Items in PCCO 20 Steel Jambs & Headers | PC-2403-0001 | Owner Change | Approved | LeMaster | AC created draft | 19000 | 1412.5 | 0 | 0 | 0 | 0
CR-2403-0026 Items in PCCO 20 Power to all FFE | PC-2403-0001 | Owner Change | Approved | Deem | AC created draft | 181542 | -20423.47 | 0 | 0 | 0 | 0
CR-2403-0026 Items in PCCO 20 Credit Liberty Fixtures | PC-2403-0001 | Owner Change | Approved | Dorsey | AC created draft | -2060.2 | 0 | 0 | 0 | 0 | 0
CR-2403-0026 Items in PCCO 20 Lintel Blocks at Windows | PC-2403-0001 | Owner Change | Approved | JTB Masonry | CO already created & approved | 2030 | 1520 | 0 | 0 | 0 | 0
CR-2403-0026 Items in PCCO 20 Water Supply flr drains | PC-2403-0001 | Owner Change | Approved | Dorsey | AC created draft | 4629.56 | 872.94 | 0 | 0 | 0 | 0
CR-2403-0026 Items in PCCO 20 Deduct Mezz Rail at TV wall | PC-2403-0001 | Owner Change | Approved | True Step | Waiting for JD to confirm which line items need to be moved out | -3722 | 0 | 0 | 0 | 0 | 0
CR-2403-0026 Items in PCCO 20 Wet Wall Tile Deduct | PC-2403-0001 | Owner Change | Approved | Market Ready | AC drafted CO, did Nick send back updated pricing? | -1600 | 0 | 0 | 0 | 0 | 0
CR-2403-0026 Items in PCCO 20 6" UG Beer Chase | PC-2403-0001 | Owner Change | Approved | Dorsey | AC drafted CO, do I need to add individual line items? | 8658.82 | 216.68 | 0 | 0 | 0 | 0
CR-2403-0026 Items in PCCO 20 Total | PC-2403-0001 | Owner Change | Approved |  |  | 223478.18 | -15870.1 | 21020.32 | 2595.1 | 231223.5 | 7745.32
CR-2403-0030 Foundation Fast Cure Mix | PC-2403-0001 | Internal | Void |  |  | 6265 | 0 | 0 | 0 | 6265 | 6265
CR-2403-0031 Merritt- Additional Stone | PC-2403-0001 | Internal | Approved |  |  | 7286 | 0 | 0 | 0 | 0 | -7286
CR-2403-0032 CDR Review | PC-2403-0004 | Owner Change | Approved |  |  | 20 | 30 | 0 | 0 | 0 | 30
CR-2403-0032 Bathroom Foundation | PC-2403-0004 | Owner Change | Approved |  |  | 3868 | 0 | 0 | 0 | 0 | 0
CR-2403-0032 Siding | PC-2403-0004 | Owner Change | Approved | LeMaster? | Check JL Construction Quote | 13500 | 0 | 0 | 0 | 0 | 0
CR-2403-0032 Doors | PC-2403-0004 | Owner Change | Approved | Not Assigned | Check JL Construction Quote | 2500 | 0 | 0 | 0 | 0 | 0
CR-2403-0032 Metal Framing/Drywall | PC-2403-0004 | Owner Change | Approved |  |  | 18000 | 0 | 0 | 0 | 0 | 0
CR-2403-0032 Tile | PC-2403-0004 | Owner Change | Approved | Not Assigned | Check JL Construction Quote | 3500 | 0 | 0 | 0 | 0 | 0
CR-2403-0032 Sealed Concrete | PC-2403-0004 | Owner Change | Approved | Call Gray Rock for CO |  | 1800 | 0 | 0 | 0 | 0 | 0
CR-2403-0032 Painting/Doors | PC-2403-0004 | Owner Change | Approved | Not Assigned | Check JL Construction Quote | 2500 | 0 | 0 | 0 | 0 | 0
CR-2403-0032 Bathroom Accessories | PC-2403-0004 | Owner Change | Approved | Not Assigned | Check JL Construction Quote | 2500 | 0 | 0 | 0 | 0 | 0
CR-2403-0032 Fire Suppression | PC-2403-0004 | Owner Change | Approved | Siemens |  | 0 | 3500 | 0 | 0 | 0 | 0
CR-2403-0032 Plumbing | PC-2403-0004 | Owner Change | Approved |  |  | 22225 | 0 | 0 | 0 | 0 | 0
CR-2403-0032 HVAC | PC-2403-0004 | Owner Change | Approved |  |  | 17000 | 0 | 0 | 0 | 0 | 0
CR-2403-0032 Electrical | PC-2403-0004 | Owner Change | Approved |  |  | 2500 | 0 | 0 | 0 | 0 | 0
CR-2403-0032 Add Volley Ball Court Bathrooms | PC-2403-0004 | Owner Change | Approved |  |  | 89913 | 3530 | 9461.14 | 1168.04 | 104072.18 | 14159.18
CR-2403-0033 Concrete in VB Courts | PC-2403-0004 | Owner Change | Approved |  |  | 48016 | 1984 | 5062.5 | 625 | 55687.5 | 7671.5
CR-2403-0034 VB Spoils Export | PC-2403-0004 | Internal | Approved |  |  | 23579 | 0 | 0 | 0 | 0 | -23579
CR-2403-0036 Deduct For Trailer Power Reconnection | PC-2403-0001 | Internal | Approved |  |  | -1545 | 0 | 0 | 0 | -1545 | 0
CR-2403-0037 OH Doors Deduct | PC-2403-0001 | Internal | Approved | Pro Garage Door | Glenn wrote in the commitments | -2532 | 0 | 0 | 0 | -2532 | 0
CR-2403-0038 Electrical Design Shortages | PC-2403-0001 | Internal | Approved |  |  | 34150 | 0 | 0 | 0 | 0 | -34150
CR-2403-0039 Added Stone For Drive and Crane Pad for Agg Piers | PC-2403-0001 | Internal | Approved |  |  | 20160 | 0 | 0 | 0 | 0 | -20160
CR-2403-0040 Extend Concrete Patio | PC-2403-0004 | Owner Change | Approved | Merritt | Glenn wrote in the commitments | 54836.86 | 5163.14 | 0 | 0 | 0 | 0
CR-2403-0040 Risers for Storm drain in Patio | PC-2403-0004 | Owner Change | Approved | United | Glenn wrote in the commitments | 1500 | 1500 | 0 | 0 | 0 | 0
CR-2403-0040 Sealed Concrete for interior slab | PC-2403-0004 | Owner Change | Approved | Gray Rock | Need to figure what this quote is for in relation to added North volleyball patio | 1200 | 800 | 0 | 0 | 0 | 0
CR-2403-0040 VB Poles | PC-2403-0004 | Owner Change | Approved |  |  | 5500 | 2000 | 0 | 0 | 0 | 0
CR-2403-0040 Concrete Patio Addition | PC-2403-0004 | Owner Change | Approved |  |  | 63036.86 | 9463.14 | 7340.63 | 906.25 | 80746.88 | 17710.02
CR-2403-0041 Concrete Contingency Pay CR 25, & CR 30 | PC-2403-0001 | Owner Change | Approved |  |  | 10569 | 0 | 0 | 0 | 0 | -10569
CR-2403-0042 HVAC Deduct to FITE | PC-2403-0001 | Internal | Approved |  |  | -201000 | 208000 | 0 | 0 | 0 | -7000
CR-2403-0043 Perimeter Trail Deduct From DPW | PC-2403-0001 | Internal | Approved |  |  | -34691.8 | 34691.8 | 0 | 0 | 0 | 0
CR-2403-0044 VB East Wall Girts and Insulation | PC-2403-0001 | Internal | Approved |  |  | 23000 | 0 | 0 | 0 | 23000 | 0
CR-2403-0044 Eliiminate Columns at GL9 & Change Rafters | PC-2403-0001 | Internal | Approved |  |  | 6800 | 0 | 0 | 0 | 6800 | 0
CR-2403-0044 Field Modify Bathroom Door | PC-2403-0001 | Internal | Approved |  |  | 1200 | 0 | 0 | 0 | 1200 | 0
CR-2403-0044 Perimeter Angle and Welded Bar | PC-2403-0001 | Internal | Approved |  |  | 34000 | 0 | 0 | 0 | 34000 | 0
CR-2403-0044 Remove Tube Support on North Endwall | PC-2403-0001 | Internal | Approved | LeMaster? | Done | -7500 | 0 | 0 | 0 | -7500 | 0
CR-2403-0044 Add Curbs for Kitchen Equipment | PC-2403-0001 | Internal | Approved |  |  | 38000 | 0 | 0 | 0 | 38000 | 0
CR-2403-0044 Mezzaniine Openings for Kitchen Ducting | PC-2403-0001 | Internal | Approved |  |  | 8000 | 0 | 0 | 0 | 8000 | 0
CR-2403-0044 LeMaster Items Left Off Subcontract | PC-2403-0001 | Internal | Approved |  |  | 103500 | 0 | 0 | 0 | 0 | -103500
CR-2403-0045 Installation of Fans Deem | PC-2403-0004 | Internal | Approved | Deem | Done | 5713.32 | 0 | 0 | 0 | 0 | 0
CR-2403-0045 PO for Big Ass Fans | PC-2403-0004 | Internal | Approved |  |  | 20140.4 | 0 | 0 | 0 | 0 | 0
CR-2403-0045 Big Ass Fans | PC-2403-0004 | Internal | Approved |  |  | 25854 | 0 | 0 | 0 | 0 | -25854
CR-2403-0046 FO Box Relocation | PC-2403-0001 | Internal | Approved |  |  | 29334 | -29334 | 0 | 0 | 0 | 0
CR-2403-0047 Site Work Contingencies | PC-2403-0001 | Owner Change | Approved |  |  | 0 | 0 | 0 | 0 | 0 | 0
CR-2403-0048 ROW Undercutting | PC-2403-0001 | Owner Change | In Review | United (inccomplete) | Andrew drafted CO | 24050 | -24050 | 0 | 0 | 0 | 0
CR-2403-0049 Leftover Design Items | PC-2403-0001 | Owner Change | Draft |  | Void | 0 | 0 | 0 | 0 | 0 | 0
CR-2403-0050 Access Panels At Beer Wall | PC-2403-0001 | Owner Change | Void |  |  | 1650 | 850 | 253.13 | 31.25 | 2784.38 | 1134.38
CR-2403-0051 Tracked Equipment Rental | PC-2403-0001 | Internal | Approved | LeMaster | Andrew drafted CO | -3623.33 | 3623.33 | 0 | 0 | 0 | 0
CR-2403-0052 Added Downspouts and Underdrains | PC-2403-0001 | Internal | In Review | United | Andrew drafted CO | 5720 | 0 | 0 | 0 | 0 | -5720
CR-2403-0053 Re-Prep SOG | PC-2403-0001 | Internal | Draft | Merritt | Andrew drafted CO, Josh Hillery sending 3 CO's Monday 10/27 | 16500 | 0 | 0 | 0 | 0 | -16500
CR-2403-0054 Fiber Optic Box Relocation | PC-2403-0001 | Owner Change | Approved |  |  | 29334 | 0 | 2970.02 | 366.67 | 32670.69 | 3336.69
CR-2403-0055 Final Permit and Inspection Fees | PC-2403-0001 | Owner Change | Draft |  |  | 225 | 22.78 | 2.81 | 0 | 250.59 | 25.59
CR-2403-0056 Breeze Blocks | PC-2403-0001 | Owner Change | Approved | JTB Masonry | Andrew drafted CO, | 10000 | -1125 | 0 | 0 | 0 | 0
CR-2403-0056 Partition Rails | PC-2403-0001 | Owner Change | Approved | True Step | Andrew Drafted the CO | 50150 | -1337.5 | 0 | 0 | 0 | 0
CR-2403-0056 High Tops | PC-2403-0001 | Owner Change | Approved | True Step | Andrew Drafted the CO | 10002 | 648 | 0 | 0 | 0 | 0
CR-2403-0056 Roof Access Ladder | PC-2403-0001 | Owner Change | Approved | True Step | Andrew Drafted the CO "attached to block wall" | 5072.5 | 0 | 0 | 0 | 0 | 0
CR-2403-0056 6 Doors Added throughout Design | PC-2403-0001 | Owner Change | Approved | CIH | PO, check counts on PO with current plans to make sure we have all doors accounted for | 0 | 7455 | 0 | 0 | 0 | 0
CR-2403-0056 Eliason Doors Upgrade | PC-2403-0001 | Owner Change | Approved | CIH | PO | 0 | 887.5 | 0 | 0 | 0 | 0
CR-2403-0056 SF Windows & Doors | PC-2403-0001 | Owner Change | Approved | Diamond Glass | Can't find quote, not sure what this is for this. Call Dave L 10/24 | 41690 | -252.62 | 0 | 0 | 0 | 0
CR-2403-0056 Windows in Nooks | PC-2403-0001 | Owner Change | Approved | CIH | PO | 0 | 1775 | 0 | 0 | 0 | 0
CR-2403-0056 Paint for added Walls | PC-2403-0001 | Owner Change | Approved | S&M | not sure what this is for. Adam is sending quote tomorrow. | 2100 | 118.75 | 0 | 0 | 0 | 0
CR-2403-0056 Framing, Tile Backer, Arches, Framng Etc | PC-2403-0001 | Owner Change | Approved | Superior | AC drafted CO | 83756 | 387 | 0 | 0 | 0 | 0
CR-2403-0056 November Design Adds | PC-2403-0001 | Owner Change | Approved |  |  | 202770.5 | 8556.13 | 21396.83 | 2641.6 | 235365.06 | 32594.56
CR-2403-0057 Casework & Millwork | PC-2403-0001 | Owner Change | Approved | Casework Concepts |  | 103354 | 908.5 | 0 | 0 | 0 | 0
CR-2403-0057 Granite Countertops | PC-2403-0001 | Owner Change | Approved | Marble Uniques | JR | 16814.87 | -59.12 | 0 | 0 | 0 | 0
CR-2403-0057 Labor, Thin Set, Grout | PC-2403-0001 | Owner Change | Approved | Market Ready | JR | 57000 | 6234.38 | 0 | 0 | 0 | 0
CR-2403-0057 Shousugiban and Ship Lap | PC-2403-0001 | Owner Change | Approved | Market Ready | JR | 21000 | 2075 | 0 | 0 | 0 | 0
CR-2403-0057 December Design Adds | PC-2403-0001 | Owner Change | Approved |  |  | 198168.87 | 9158.76 | 20991.92 | 2591.6 | 230911.15 | 32742.28
CR-2403-0059 RTU Curb Reinforcement for Screens | PC-2403-0001 | Internal | In Review | LeMaster | JR | 17610 | 0 | 0 | 0 | 0 | -17610
CR-2403-0060 LeMaster Tickets | PC-2403-0001 | Internal | In Review | LeMaster | JR | 5193 | 0 | 0 | 0 | 0 | -5193
[7 empty] | 186608.27 | 129897.18 | 16036.38 | 1527723.49 | -87460.69