## Door, Frame, HDWR delivery
Notes
Opening | Door | Frame | Hardware | Notes
100A | yes | yes
100B | No | No
101A | yes | yes
102 | yes | yes
104 | yes | yes
105 | yes | yes
106 | yes | yes
107 | yes | yes
108 | Yes | yes
111 | yes
EX 111 | Yes | Yes
112 | yes | No |  | at CIH
113 | Vendor Spaces not getting doors?
114
115
116
117
118A | yes | yes
118B | yes | yes
121 | yes | yes
122 | yes | yes
123 | yes(x2) |  |  | 10 business days from 11/12, ask Vivian for update | Confirm jamb depth, head size, and anchoring for 121,122,123A,B,C,&D. 5 3/4" Jamb Depth, Multipurpose anchors and 2" studs ?
123A | yes(x2)
123B | yes(x2)
123C | yes(x2)
123D | yes | yes |  | Volleyball bathrooms EX door?
126 | 11/21 or 11/24 | yes |  | Frames were ordered as welded should've been KD | Andrew notified CIH 11/24
127 | 11/21 or 11/24 | yes
EX106 | yes | yes
EX108 | yes | yes
OH101A | yes | yes
OH101B | yes | yes
OH102 | Yes | Yes
OH103 | Yes | Yes
OH118A | Yes | yes
OH118B | Yes | yes
OH123A | Yes | Yes
OH123B | Yes | Yes
OH123C | Yes | Yes
Second LVL
200A | Yes | yes
200B | Yes | yes
200C | Yes | yes
202 | yes | yes
203 | yes | yes
204 | yes | yes
205 | yes | yes
206 | yes | yes
207 | yes | yes
208 | yes | yes
210 | yes | yes
213 | yes | yes |  | Andrew to confirm if door is onsite 11/24
214 | yes | yes |  | CIH will be on site today to install 12/04/2025
OH201A | Yes | Yes
OH201B | Yes | Yes

## Sheet2
Accessories, Plumbing, Finishes, Lighting
Product Type | Product | Date Needed For Install
Bathroom Mirror | Accessories | 2026-01-07
Plumbing Fixtures

## DGI 10.28.25 Pricing Update
DGI Interior Design Updates 10/28/2025
Floor Finish Private Room: Left Over Laminate Flooring
Task |  | Subcontractor |  | Add or Credit | Received?
Labor to install LVT |  | MKT Ready |  | Add | Yes
Labor to install wall base |  | MKT Ready |  | Add | No
Floor transition from SF |  | Diamond Glass |  | Add | No
Reduced tile height in Ice Cream from 4' to 3'
Task |  | Subcontractor |  | Add or Credit | Received?
Reduce Tile Backer |  | Superior |  | Credit | Yes
Labor |  | MKT Ready |  | Credit | Yes
Added tile to Beer Wall, eliminated Shou-Sugi Ban
Task |  | Subcontractor |  | Add or Credit | Received?
SSB Labor |  | MKT Ready |  | Credit | Yes
Install Tile Labor |  | MKT Ready |  | Add | Yes
Install Tile Backer |  | Superior |  | Add | Yes
Added tile under unisex sinks
Task |  | Subcontractor |  | Add or Credit | Received?
Install Tile Backer |  | Superior |  | Add | Yes
Install Tile Labor |  | MKT Ready |  | Add | Yes
Added Wallpaper for nooks
Task |  | Subcontractor |  | Add or Credit | Received?
Install Wallpaper |  | Vertex Painting |  | Add | Yes
MKT Ready | Vertex Painting | Superior
16550 | 2100 | 875 | 3725
2850
Total | 19525 | If no wallpaper is installed on ceilings
or
| 20275 | If wallpaper is installed on ceilings

## Sheet1
Owner's Walk Changes 11.12.25
Task | Subcontractor | Add or Credit | Received?
3 Exterior Gooseneck Lights | DEEM | Add | Yes
Install 30" door at beer wall | Superior | Add | No
Remove 3 access panels at beer wall | Superior | Credit | No
Remove ACT Ceilings in Walk in Cooler area | Superior | Credit
Add Bulkhead at Walk in Cooler are | Superior | Add
Added concrete (demo curb) at main entrance | Merritt | Add
Add Beer Wall on 2nd level | TBD | Add
Added metal post and chain for converted coffee bar to Bourbon Bar | TBD | Add
Reduce TV's at 2nd floor bar from 10 to 5 Tvs | TBD
Routed channgels in bartops for drink rail | TBD | Add?

## Owner Provided Items
Main Level |  |  |  |  | Second Level
Casework Schedule - Main Level |  |  |  |  | Casework Schedule - Second Level
Label | Description | Location | Provided By | Notes | Label | Description | Location | Provided by | Notes
C-01 | L-Shaped Banquette | DNG 123 | Alleato |  | C-03 | Linear Banquette | STG 200 + 202 | Alleato
C-02 | Linear Banquette | DNG 118 | Alleato |  | C-04 | Booths | STG 201 +203 | Alleato
C-06 | Trash & Coke Machine | Along Stairs | Alleato |  | C-05 | Nook Booths | Nooks | Alleato
C-06.A | Trash & Coke Machine Mirrored | Along Stairs | Alleato |  | C-06 | Trash & Coke Machine | STG 203 | Alleato
C-07 | Small Trash Receptacle | DNG 123 | Alleato | One one first level Alleato will provide | C-07 | Small Trash Receptacle | STG 201 & 203 | Mike | Two C-07 on second level Mike is providing
C-09 | Host Stand - Customer Side | Lobby | Alleato |  | C-08 | Large Trash Receptacle | STG 201 | Alleato
C-09.A | Host Stand - Staff Side | Lobby | Alleato
C-10 | Beer Wall Low Cabinets | Beer Wall | Alleato |  | Metal Work Schedule - Second Level
C-11 | Beer Wall Shallow Tall Cabinet | Beer Wall | Alleato |  | Label | Description | Location | Provided by | Notes
[5 empty] | M-02 | Picnic Table (Bench Separate) | Covered Patio | Mike
Metalwork Schedule - Main Level |  |  |  |  | M-02.A | Picnic Bench | Covered Patio | Mike
Label | Description | Location | Provided by | Notes | M-03 | Hightop Base - 6 top | Seating 200 & Patio | Mike
M-01 | Picnic Table | Covered Patio | Mike |  | M-03.A | Indoor Tabletop - 6 top | Seating 200 | Mike
M-04 | Hightop Base - 8 Top | Dinning 123 | Mike |  | M-03.B | Outdoor Tabletop - 6 top | Covered Patio | Mike
M-04.A | Indoor Tabletop - 8 Top | Dinning 123 | Mike |  | M-04 | Hightop Base - 8 top | Seating 201 & Patio | Mike
M-05 | Hightop Table W/Base - 10 Top | Bar 103 | Mike |  | M-04.A | Indoor Tabletop - 8 Top | Seating 201 | Mike
M-08 | Drink Rail | Dinning 118 | Alleato |  | M-04.B | Outdoor Tabletop - 8 Top | Covered Patio | Mike
M-10 | Alcohol Rail Bar 103 South | Bar 103 | Alleato |  | M-04.C | Indoor Light Mount - 8 Top | Seating 201 | Mike
M-11 | Alcohol Rail Bar 103 North | Bar 103 | Alleato |  | M-05 | Hightop Table/ Base -10 Top | Seating 202 | Mike
M-12 | Alcohol Rail Bar 103 East | Bar 103 | Alleato |  | M-06 | Hightop Table/Base - 5 Top | Covered Patio | Mike
M-13 | Alcohol Rail Outside Bar | Bar 103 | Alleato |  | M-07 | Mezzanine Drink Rail | Seating 200 | Alleato
M-14 | Alcohol Rail Bar Beer Wall | Beer Wall | Alleato |  | M-09 | Acohol Rail Bar 201 South | Bar 201 | Alleato
M-15 | TV Mount - Bar 103 | Bar 103 | Mike |  | M-13 | Alcohol Rail Bar Outside | Bar 201 Covered Patio | Alleato
[5 empty] | M-16 | TV Mount - Bar 201 | Bar 201 | Mike
Furniture Schedule - Main Level
Label | Description | Location | Provided By | Notes | Furniture Schedule - Second Level
F-01 | Table Top 30 X 30 | All, Interior | Mike |  | Label | Description | Location | Provided By | Notes
F-01.A | Table Base 30 X 30 | All, Interior | Mike |  | F-01 | Table Top 30 x 30 | All, Interior | Mike
F-02 | Table Top 36R | All, Interior | Mike |  | F-01.A | Tabel Base 30 X 30 | All, Interior | Mike
F-02.A | Table Base 36R STD Height | All, Interior | Mike |  | F-02 | Table Top 36R | All, Interior | Mike
F-03 | Table Top 54 x 30 | All, Interior | Mike |  | F-02.B | Table Base 36R Bar Height | All, Interior | Mike
F-03.A | Table Base 54 x 30 | All, Interior | Mike |  | F-03.A | Table Top 54 x 30 | All, Interior | Mike
F-07 | Chair | All, Interior | Mike |  | F-04 | Table Base 54 x 30 | All, Interior | Mike
F-08 | Bar Stool | All, Interior | Mike |  | F-05 | Table Top 72 x 30 | All, Interior | Mike
F-17 | Outdoor Table Top 30 X 30 | Covered Patio | Mike |  | F-06 | Table Top 84 x 36 | All, Interior | Mike
F-17.A | Outdoor Table Base 30 X 30 | Covered Patio | Mike |  | F-07 | Table Base 72 x 30 & 84 x 36 | All, Interior | Mike
F-19 | Outdoor Chair | Covered Patio | Mike |  | F-08 | Chair | All, Interior | Mike
F-20 | Outdoor Bar Stool | Covered Patio | Mike |  | F-09 | Bar Stool | All, Interior | Mike
F-21 | Outdoor Sofa | Covered Patio | Mike |  | F-10 | Sofa Large | Seating 201 & Nooks | Mike
F-24 | Outdoor Adirondack Chairs | Outside, Not shown on plan | Mike |  | F-11 | Sofa Medium | Seating 200 & 201 | Mike
F-24 | Outdoor Coffe Table SQ | Covered Patio | Mike |  | F-12 | Side Chair | Center Nook | Mike
F-26 | Outdoor Planter RECT | Covered Patio | Mike |  | F-13 | Coffee Table 48 x 24 | Seating 201 & Nooks | Mike
F-27 | Outdoor Planter Round | Covered Patio | Mike |  | F-14 | Coffee Table 48 x 18 | Seating 200 | Mike
F-28 | Outdoor Trash Cans | Covered Patio | Mike |  | F-15 | Coffee Table 30 x 30 | Seating 200 | Mike
[5 empty] | F-16 | POUF | Seating 200 | MIke
Accessories Schedule - Main Level |  |  |  |  | F-17 | Console Table | Covered Patio | Mike
Label | Description | Location | Provided By | Notes | F-17.A | Outdoor Table Top 30 x 30 | Covered Patio | MIke
M-01 | Restroom Vanity Mirrior | Womens RR | Mike |  | F-19 | Outdoor Table Base 30 x 30 | Covered Patio | Mike
M-02 | Restroom Vanity Mirror | Men's RR + Common Sink | Mike |  | F-20 | Outdoor Bar Stool | Covered Patio | Mike
[5 empty] | F-21 | Outdoor SOFA | Covered Patio | Mike
[5 empty] | F-22 | Outdoor Side Chair | Covered Patio | Mike
[5 empty] | F-25 | Outdoor Coffee Table 48 x 24 | Covered Patio | Mike
[5 empty] | F-26 | Outdoor Planters 60 x 30 | Covered Patio | Mike
[5 empty] | F-28 | Outdoor Trash Cans | Covered Patio | Mike
[5 empty] | F-29 | Folding Table - 48R | Private Rooms | Mike
[5 empty] | F-03 | Table Top 54 x 30 | All, Interior | Mike
Accessories Schedule - Second Level
[5 empty] | Label | Description | Location | Provided By | Notes
[5 empty] | M-01 | Restroom Vanity Mirror | Womens RR | Mike
[5 empty] | M-02 | Restroom Vanity Mirror | Men's RR + Common Sink | Mike
[5 empty] | AR-01 | Rug 1 Oriental, RED | Seating 200 | Mike
[5 empty] | AR-02 | Rug 2 Oriental, Blue | Seating 200 | Mike
[5 empty] | AR-03 | Rug 3 Oriental, Grey | Seating 200 | Mike
[5 empty] | AR-04 | Rug 4 Oriental, Brown | Seating 200 | Mike
[5 empty] | AR-05 | Rug 5 Oriental, B&W | Seating 200 | Mike
[5 empty] | AR-06 | Rug 6 Oriental, Grey | Seating 200 | Mike

## Utility Tracker
Westfield Collective Utility Accounts
Service/ Provider | Contact Name | Contact # | Entity Name(S) | Status | Notes | Attachments
CenterPoint (Gas) | TBD | 1-800-990-1930 | TBD | Off | CenterPoint will be onsite 11/13/2025 to turn gas on
Duke (Electric) | TBD | TBD | TBD | Off | Transformer is on backorder. Anticipate install mid December.
Citizens (Water/Sewer) | TBD | 317-924-3341 | TBD | Off | 317-927-4444, AC to call 10/13/2025

## Change Order Status
| Review with Brandon or Chad |  |  |  | Review with Jesse Dawson
Change Order Tracker
CR # | CCO # | Company Name | Amount | Sent to Sub Date | Sent? | Exeucted ? | Notes
| CCO-0063 | Mkt Ready | -7200 | 2025-10-28 | Yes | No
| CCO-0059 | Superior | 83756 | 2025-10-28 | Yes | No
| CCO-0062 | Superior | 1320 | 2025-10-28 | Yes | No
| CCO-0066 | S&M Paint | 2100 | 2025-10-28 | Yes | No | Adamn sent back 10/29
| CR-0060 | LeMaster | 5192 | - | No | No | Andrew to send out LeMaster tickets to associated sub PMs for their review.
| CCO-0050 | CIH | 2385.44 | - | No | No | Andrew to review CIH shop drawings prior to ordering
| CCO-0069 | LeMaster | 17610 | - | Yes | No | Nick sent back signed 10/29/2025
| CCO-0067 | Marble Uniques | 16814.87 | - | No | No | Change order is included in their contract amount
| CCO-0058 | True Step | 3300 | - | Yes | No
| CCO-0057 | True Step | 10002 | - | No | No | Waiting for Mike to confirm Metalwork Markup (Sent 10/27)
| CCO-0056 | True Step | 50150 | - | No | No | Waiting for Mike to confirm Metalwork Markup (Sent 10/27)
| CCO-0055 | JTB Masonry | 10000 | 2025-10-30 | Yes | No
| CCO-0054 | Merritt | 24302.5 | 2025-10-29 | Yes | No
| CCO-0053 | United Excavating | 5720 | 2025-10-28 | Yes | No | Ryan sent back signed on 10/29/2025
| CCO-0064 | United Excavating | 9440 | 2025-10-28 | Yes | No | Ryan sent back signed on 10/29/2025
| CCO-0051 | United Excavating | 14610 | 2025-10-29 | Yes | No | South A/D Lane Undercut.
CR-40 | CCO-0049 | Grey Rock | 1800 | Glenn already sent | No | No | This was a CO for the added VB bathrooms. Glenn signed it, but Grey Rock has not. Glenn was trying to get sealer and traction additive in the entire building. Contract accounts for that. Need deductive CO written. Just need Jason to sign and return?
CR-38 | CCO-0030 | DEEM | TBD |  | No |  | Which price do I used?
CR-36 | CCO-0021 | DEEM | -1545 | 2025-10-29 | Yes | No
CR-66 | CCO-0028 | C&S | 23650 | 2025-10-29 | Yes | No
CR-65 | CCO-70 | Merritt | 2270 |  | No | No | dispute labor and finisher rates… 70 & 80 an hour.
CR-34 | CCO-0025 | United Excavating | 5500 | 2025-10-29 | No
CR-64 | CCO-0065 | Diamond Glass | -1915 | 2025-10-30 | Yes | No
CR-68 | CCO-0073 | CIH | 606.69 | 2025-11-04 | Yes | No | Sent follow up email 11/11/2025
CR-68 | CCO-0074 | DKM (CIH) | 606.69 | 2025-11-04 | Yes | Yes | Sent follow up email 11/11/2025
CR-26 | CCO-044 | LeMaster | 19000 | 2025-11-10 | Yes | Yes | LeMaster requested Andrew C to email CO-044 so both parties could sign. LeMaster had already receiveced payment but did not have a executed copy.

## Budget Modifications
Budget Modifications
Cost Code | Cost Code Name | Contract Change Order | Projected Over/Under | Money Moved From | Notes
237000 | Central HVAC Equipment |  | 23650 | Unallocated Costs | AC pushed to ERP on 11/03/2025 & added Executed CO
312316 | Excavation |  | 14610 | TBD | Ryan (United PM) will send back signed CO 11/3.
550099 | Unallocated Cost | 9135.87 | N/A | N/A | AJ found, should not have been pulled from Unallocated costs. Is this an error? Is Alleato supposed to be covering?

## Procurement Log
Project |  |  | Westfield Collective
Address |  |  | 750 E 181st ST Westfield, IN 46074
Material/Procurement Log:
Material | Submittal | Supplier / Manufacturer | Responsibility | Contact Name | Contact Number | Contact Email | Quantity | Lead Time | Date Needed on Site | Date Submitted | Date Approved | Date Ordered | Est. Delivery Date | Actual Delivery Date | Comments
LeMaster Steel
Anchor Rods | 05-1 | LeMaster | Chad | Nick Bigler | (317) 495-5303 | nbigler@lemastersteel.com | All | 5 Days | 2025-05-23 | 2025-04-09 | 2025-04-23 | 2025-05-01 | 2025-05-27 | 2025-05-27
Structural Steel | 05-2 | LeMaster | Glenn | Nick Bigler | (317) 495-5303 | nbigler@lemastersteel.com | All | 60 Days | 2025-06-23 | 2025-04-11 |  | 2025-02-28 | 2025-06-18 | 2025-06-23
FG Schaefer Co
Commissary Equipment | 11-02 | FG Schaefer Co | Glenn | Daniel Stewart | (513) 254-4525 | dstewart@fgschaefer.com |  | Sent Email 05/28/2025 | 2025-10-22 | 2025-03-03 |  | 2025-09-01 | Waiting for update from Daniel
Bar Equipment | 11-03 | FG Schaefer Co | Glenn | Daniel Stewart | (513) 254-4525 | dstewart@fgschaefer.com |  | Sent Email 05/28/2025 | 2025-10-22 |  |  | 2025-09-01 | Waiting for update from Daniel
Ice Cream Bar Equipment | 11-04 | FG Schaefer Co | Glenn | Daniel Stewart | (513) 254-4525 | dstewart@fgschaefer.com
Wine Bar Equipment | 11-05 | FG Schaefer Co | Glenn | Daniel Stewart | (513) 254-4525 | dstewart@fgschaefer.com |  | Sent Email 05/28/2025 | 2025-10-22 | 2025-03-06 |  | 2025-09-01 | Waiting for update from Daniel
Roberto and Miguels | 11-06 | FG Schaefer Co | Glenn | Daniel Stewart | (513) 254-4525 | dstewart@fgschaefer.com |  | Sent Email 05/28/2025 | 2025-10-22 | 2025-03-03 |  | 2025-09-01 | Waiting for update from Daniel
Lei Lie's | 11-07 | FG Schaefer Co | Glenn | Daniel Stewart | (513) 254-4525 | dstewart@fgschaefer.com |  | Sent Email 05/28/2025 | 2025-10-22 | 2025-03-03 |  | 2025-09-01 | Waiting for update from Daniel
Bristols | 11-08 | FG Schaefer Co | Glenn | Daniel Stewart | (513) 254-4525 | dstewart@fgschaefer.com |  | Sent Email 05/28/2025 | 2025-10-22 | 2025-03-03 |  | 2025-09-01 | Waiting for update from Daniel
Stir | 11-09 | FG Schaefer Co | Glenn | Daniel Stewart | (513) 254-4525 | dstewart@fgschaefer.com |  | Sent Email 05/28/2025 | 2025-10-22 | 2025-03-03 |  | 2025-09-01 | Waiting for update from Daniel
Zaria | 11-10 | FG Schaefer Co | Glenn | Daniel Stewart | (513) 254-4525 | dstewart@fgschaefer.com |  | Sent Email 05/28/2025 | 2025-10-22 | 2025-03-03 |  | 2025-09-01 | Waiting for update from Daniel
WIC Condenser | 11-01 | FG Schaefer Co | Glenn | Daniel Stewart | (5153) 254-4525 | dstewart@fgschaefer.com |  |  |  | 2025-03-06 |  |  | Waiting for update from Daniel
Hoods/Exhaust Fans (kitchen) |  | Captive Aire/ FG Schaefer | Glenn | Daniel Stewart | (513) 254-4525 | dstewart@fgschaefer.com |  | Sent Email 05/28/2025 | 2025-10-03 |  |  | 2025-09-01 | Waiting for update from Daniel
C&S
Volleyball Space Heaters | 23-1 | C&S | Glenn | Jeff Christof |  | jrchristoff@yahoo.com |  |  | 2025-08-27 |  |  |  | installed
RTU's | 23-2 | FITE | Glenn | Erika Fraits | (317) 610-6371 | erikaf@fitellc.com | 4 | 55 | 2025-08-12 | 2025-03-04 | 2025-04-30 |  | onsite |  | Will be delivered either last week of July or first week of August
Air Curtains | 23-6 | C&S | Glenn | Jeff Christof |  | jrchristoff@yahoo.com |  |  | 2025-11-20 |  |  |  | Waiting for update from Jeff
BAF's | 26-3 | C&S | Glenn | Jeff Christof |  | jrchristoff@yahoo.com | 2 |  | 2025-10-15 |  |  |  | 2025-10-09
Mini Splits (Volleyball Bathroom)
Heaters |  | C&S | Glenn | Jeff Christof |  | jrchristoff@yahoo.com |  | 20 | 2025-08-29 |  |  |  | Waiting for update from Jeff
Mechanical Screen |  | C&S | Andrew | Jeff Christof |  | jrchristoff@yahoo.com | 4 (units) | 6 weeks | 2025-12-05 | TBD (as of 10/20/2025) | TBD (as of 10/20/2025) | TBD | 2025-12-05 |  | Jeff is waiting for units to be installed prior to ordering.
DEEM
Site Lightings/ Exterior lighting | 26-1 | DEEM | Glenn | Brennan Rhoades | 7657480973 | brhoades@deemfirst.com |  | 60 | 2025-10-30 |  |  | In stock | In stock
2nd Floor Interior Lighting | 26-2 | DEEM | Glenn | Brennan Rhoades | 7657480973 | brhoades@deemfirst.com |  | Sent Email 05/28/2025 | 2025-10-28 |  |  | In stock | In stock
1st Floor Interior Lighting |  |  | Glenn | Brennan Rhoades | (765) 748-0973 | brhoades@deemfirst.com |  | Sent Email 05/28/2025 | 2025-12-04 |  |  | In stock | In stock
Transformer |  |  | Andrew | Brennan Rhoades | (765) 748-0973 | brhoades@deemfirst.com |  | Sent Email 10/6/2025 | 2025-10-17 |  |  |  | 2025-11-04 |  | Robert & Alex with DEEM are to provide an update
Big A$$ Fans |  |  | Glenn | Waiting on Glenn | Waiting on Glenn | Waiting on Glen |  | Tbd | 2025-10-13 |  |  |  | 2025-10-09
Justin Dorsey
2nd Floor Plumbing Fixtures and Fittings | 22-1 | Justin Dorsey | Glenn | Tom Tinkle | (317) 751-2590 | Tom@justindorseyplumbing.com |  | 3 days (Stock Items) | 2025-10-08 |  | 2025-05-05 |  | 2025-10-08
1st Floor Plumbing and Fittings | 22-1 | Justin Dorsey | Glenn | Tom Tinkle | (317) 751-2590 | Tom@justindorseyplumbing.com |  | 3 days (Stock Items) |  |  |  |  | 2025-10-08
Diamond Glass
Glass | 08-1 | Diamond Glass | Glenn | David Driscoll | 317-951-4700 | driscoll@diamondglassworks.net |  | 15 | 2025-10-13 | not complete | not complete | not complete |  | 2025-10-06 | will have to order new glass due to field differences
Storefront | 08-2 | Diamond Glass | Glenn | David Driscoll | 317-951-4700 | driscoll@diamondglassworks.net |  | 25 | 2025-10-13 | not complete | not complete | not complete |  | 2025-10-06 | Arrived at Diamond Glasses shop
Executive Elevator
Elevator Equip |  | Executive Elevator |  | JW Moore | (317) 696-0471 | jwm@exelevator.com |  | 14 (weeks) | 2025-10-13 | 2025-04-18 | 2025-04-23 | 2025-05-29 | Week of 10/6-10/10 | 2025-10-06 | Arrived at Executive Elevators shop
Merritt Contracting
Bollards | 05-7 | Alleato Group | Chad | Chad Tragesser | 765-480-0703 | ctragesser@alleatogroup.com | 4 | 0 | 2025-06-27 |  |  |  | installed
True Step
Interior Stairs | 05-4 | True Step | Andrew | Tim Sutter | (513) 600-7392 | tims@truestepllc.com | 3 | 45 | 2025-10-08 |  |  |  | 2025-09-01 | 2025-10-08
Exterior Stairs |  | True Step | Andrew | Tim Sutter | (513) 600-7392 | tims@truestepllc.com |  |  | TBD |  |  |  | 2025-10-03 | 2025-10-08
Railing
Awning Partners
Metal Awning | 05-6 | Awning Partners | Andrew | Kyle Shelton | (317) 614-0584 | kyle@awningpartners.com | 1 | 60 | 2025-10-27 | 2025-04-16 | 2025-04-24 | 2025-04-24 | 2025-10-27 |  | Follow up on 7/1/2025 that awnings are in Fab.
Professional Garage Door Systems, Inc.
OH Doors | 08-3 | Professional Garage Door Systems, Inc. | Andrew | David Biddle | 3178393050 | Dbiddle@ProDoorSystems.com |  | 5-6 weeks | 2025-09-30 | 2025-05-07 |  |  | 2025-09-30 |  | 07/10, released but not ordered yet. Need door submittal (Glenn notified on 07/10)
Counter Shutters |  | Professional Garage Door Systems, Inc. | Andrew | David Biddle | (317) 839-3050 | Dbiddle@ProDoorSystems.com |  | 5-6 weeks
North Indy Fence Deck & Rail
Enclosure Gates | 05-09 | North Indy Fence Deck & Rail | Glenn | Bob Ray | (317) 848-8814 | bob@northindyfence.com | 2 | 1 week | 2025-11-10 |  |  |  | 2025-10-17 |  | Spoke to Bob Ray on 10/08/2025
Gate Posts | N/A | North Indy Fence Deck & Rail | Glenn | Bob Ray | (317) 848-8814 | bob@northindyfence.com | 3 | in stock | 2025-06-26 |  |  | 2025-06-18 | 2025-06-26 | 2025-07-03 | installed
Damn Good Interiors
2nd Floor Furniture/ Seating | 12-6 | FG Schaefer Co | Glenn | Daniel Stewart | (513) 254-4525 | dstewart@fgschaefer.com |  | Sent Email 05/28/2025 | 2025-11-14 |  |  | 2025-09-01 | Waiting for update from Daniel
1st Floor Furniture/Seating |  | FG Schaefer Co | Glenn | Daniel Stewart | (513) 254-4525 | dstewart@fgschaefer.com |  | Sent Email 05/28/2025 | 2026-01-07 |  |  | 2025-09-01 | Waiting for update from Daniel
2nd Floor Exterior Patio Furniture/ Seating | 12-7 | FG Schaefer Co | Glenn | Daniel Stewart | (513) 254-4525 | dstewart@fgschaefer.com |  | Sent Email 05/28/2025 | 2025-10-06 |  |  | 2025-09-01 | Waiting for update from Daniel
1st Floor Exterior Patio Furniture/ Seating | 12-7 | FG Schaefer Co | Glenn | Daniel Stewart | (513) 254-4525 | dstewart@fgschaefer.com |  | Sent Email 05/28/2025 | 2025-10-06 |  |  | 2025-09-01 | Waiting for update from Daniel
CIH
Exterior Doors | 08-04 | CIH | Andrew | Vivian Husband | 317-498-2593 | husbandv@cih-inc.com |  | 7 weeks | 2025-10-10 | 2025-08-18 | 2025-08-25 | 2025-08-25 | 2025-10-23 |  | Will have delivery date by 10/10
Exterior Frames | 08-04 | CIH | Andrew | Vivian Husband | 317-498-2593 | husbandv@cih-inc.com |  | 12 weeks | 2025-11-21 | 2025-08-18 | 2025-08-25 | 2025-08-25 | 2025-10-16 |  | In Stock
Exterior Door Hardware | 08-04 | CIH | Andrew | Vivian Husband | 317-498-2593 | husbandv@cih-inc.com |  | 10 weeks | 2025-11-21 | 2025-08-18 | 2025-08-25 | 2025-08-25 | 2025-10-23 |  | Will have delivery date by 10/10
Interior Frames | 08-04 | CIH | Andrew | Vivian Husband | 317-498-2593 | husbandv@cih-inc.com |  |  |  |  | 2025-08-25 | 2025-08-25 | 2025-10-23
Interior Doors & Hardware |  |  | Andrew | Vivian Husband | 317-498-2593 | husbandv@cih-inc.com |  |  |  |  | 2025-08-25 | 2025-08-25 | 2025-10-30
Div-10 | 10-1 | CIH | Andrew | Mandi Boyer | (317) 914-7323 | boyera@cih-inc.com |  | In stock |  |  |  | In stock | 2025-11-20
Bathroom Partitions |  | CIH | Andrew | Mandi Boyer | (317) 914-7323 | boyera@cih-inc.com |  | 4 weeks | 2025-11-20 |  |  | TBD | 2025-11-24
Superior
Studs | 09-1 | Superior | Glenn | Brian Jones | (317) 354-0460 | BrianJ@indysuperior.com |  | In Stock | 2025-09-29 |  |  |  |  | On Site
Drywall | 09-4 | Superior | Glenn | Brian Jones | (317) 354-0460 | BrianJ@indysuperior.com |  | In Stock | 2025-11-05 |  |  |  |  | andrew will confirm with Aaron on 10/8
1st & 2nd Floor ACT Tile | 09-3 | Superior | Glenn | Brian Jones | (317) 354-0460 | BrianJ@indysuperior.com |  | In Stock | 2025-11-26 |  |  |  |  | andrew will confirm with Aaron on 10/8
VB ACT Tile | 09-3 | Superior | Glenn | Brain Jones | (317) 354-0460 | BrianJ@indysuperior.com |  | In Stock | 2025-10-06 |  |  |  |  | andrew will confirm with Aaron on 10/8
Unknown
Mechanical Screen |  | Unkown | [6 empty] | 2025-08-07
| 08-6 | Unkown | [6 empty] | 2025-09-25
| 09-3 | Unkown | [6 empty] | 2025-10-21
| 09-3 | Unkown | [6 empty] | 2025-11-18
Bathroom Tile | 09-7 | Unkown | [6 empty] | 10/28 Level 1 12/2/2025 Level 2
Wine/Coffee Bar Tile | 09-7.1 | Unkown
Ice Cream Tile | 09-7.2 | Unkown
Bathroom Accessories | 10-2 | Unkown
Interior Signage | 10-3 | Unkown
Bike Rack | 10-5 | Amazon | Chad | install Merritt | 765-480-0703 | ctragesser@alleatogroup.com | 1 | 7 | 2025-09-09 | 2025-06-20 | 2025-06-20 |  | Waiting for update from install
Volleyball Post Sleeves |  | Unkown | Bart | Bart Conners | 317-753-2899 |  | 8 |  | 2025-09-29 |  |  |  | Waiting for update from Bart
Track light 47
Antler 17
Jelly smoke 22
OP-0Illuminate vintage cumstom 5