## Sheet1
Project |  |  | Westfield Collective
Address |  |  | 750 E 181st ST Westfield, IN 46074
Material/Procurement Log:
Material | Submittal | Supplier / Manufacturer | Responsibility | Contact Name | Contact Number | Contact Email | Quantity | Lead Time | Date Needed on Site | Date Submitted | Date Approved | Date Ordered | Est. Delivery Date | Actual Delivery Date | Comments
LeMaster Steel
Anchor Rods | 05-1 | LeMaster | Chad | Nick Bigler | (317) 495-5303 | nbigler@lemastersteel.com | All | 5 Days | 2025-05-23 | 2025-04-09 | 2025-04-23 | 2025-05-01 | 2025-05-27 | 2025-05-27
Structural Steel | 05-2 | LeMaster | Glenn | Nick Bigler | (317) 495-5303 | nbigler@lemastersteel.com | All | 60 Days | 2025-06-23 | 2025-04-11 |  | 2025-02-28 | 2025-06-18 | 2025-06-23
FG Schaefer Co
Commissary Equipment | 11-02 | FG Schaefer Co | Glenn | Daniel Stewart | (513) 254-4525 | dstewart@fgschaefer.com |  | Sent Email 05/28/2025 | 2025-10-22 | 2025-03-03 |  | 2025-09-01 | Waiting for update from Daniel
Bar Equipment | 11-03 | FG Schaefer Co | Glenn | Daniel Stewart | (513) 254-4525 | dstewart@fgschaefer.com |  | Sent Email 05/28/2025 | 2025-10-22 |  |  | 2025-09-01 | Waiting for update from Daniel
Ice Cream Bar Equipment | 11-04 | FG Schaefer Co | Glenn | Daniel Stewart | (513) 254-4525 | dstewart@fgschaefer.com
Wine Bar Equipment | 11-05 | FG Schaefer Co | Glenn | Daniel Stewart | (513) 254-4525 | dstewart@fgschaefer.com |  | Sent Email 05/28/2025 | 2025-10-22 | 2025-03-06 |  | 2025-09-01 | Waiting for update from Daniel
Roberto and Miguels | 11-06 | FG Schaefer Co | Glenn | Daniel Stewart | (513) 254-4525 | dstewart@fgschaefer.com |  | Sent Email 05/28/2025 | 2025-10-22 | 2025-03-03 |  | 2025-09-01 | Waiting for update from Daniel
Lei Lie's | 11-07 | FG Schaefer Co | Glenn | Daniel Stewart | (513) 254-4525 | dstewart@fgschaefer.com |  | Sent Email 05/28/2025 | 2025-10-22 | 2025-03-03 |  | 2025-09-01 | Waiting for update from Daniel
Bristols | 11-08 | FG Schaefer Co | Glenn | Daniel Stewart | (513) 254-4525 | dstewart@fgschaefer.com |  | Sent Email 05/28/2025 | 2025-10-22 | 2025-03-03 |  | 2025-09-01 | Waiting for update from Daniel
Stir | 11-09 | FG Schaefer Co | Glenn | Daniel Stewart | (513) 254-4525 | dstewart@fgschaefer.com |  | Sent Email 05/28/2025 | 2025-10-22 | 2025-03-03 |  | 2025-09-01 | Waiting for update from Daniel
Zaria | 11-10 | FG Schaefer Co | Glenn | Daniel Stewart | (513) 254-4525 | dstewart@fgschaefer.com |  | Sent Email 05/28/2025 | 2025-10-22 | 2025-03-03 |  | 2025-09-01 | Waiting for update from Daniel
WIC Condenser | 11-01 | FG Schaefer Co | Glenn | Daniel Stewart | (5153) 254-4525 | dstewart@fgschaefer.com |  |  |  | 2025-03-06 |  |  | Waiting for update from Daniel
Hoods/Exhaust Fans (kitchen) |  | Captive Aire/ FG Schaefer | Glenn | Daniel Stewart | (513) 254-4525 | dstewart@fgschaefer.com |  | Sent Email 05/28/2025 | 2025-10-03 |  |  | 2025-09-01 | Waiting for update from Daniel
C&S
Volleyball Space Heaters | 23-1 | C&S | Glenn | Jeff Christof |  | jrchristoff@yahoo.com |  |  | 2025-08-27 |  |  |  | installed
RTU's | 23-2 | FITE | Glenn | Erika Fraits | (317) 610-6371 | erikaf@fitellc.com | 4 | 55 | 2025-08-12 | 2025-03-04 | 2025-04-30 |  | onsite |  | Will be delivered either last week of July or first week of August
Air Curtains | 23-6 | C&S | Glenn | Jeff Christof |  | jrchristoff@yahoo.com |  |  | 2025-11-20 |  |  |  | Waiting for update from Jeff
BAF's | 26-3 | C&S | Glenn | Jeff Christof |  | jrchristoff@yahoo.com | 2 |  | 2025-10-15 |  |  |  | 2025-10-09
Mini Splits (Volleyball Bathroom)
Heaters |  | C&S | Glenn | Jeff Christof |  | jrchristoff@yahoo.com |  | 20 | 2025-08-29 |  |  |  | Waiting for update from Jeff
Mechanical Screen |  | C&S | Andrew | Jeff Christof |  | jrchristoff@yahoo.com | 4 (units) | 6 weeks | 2025-12-05 | TBD (as of 10/20/2025) | TBD (as of 10/20/2025) | TBD | 2025-12-05 |  | Jeff is waiting for units to be installed prior to ordering.
DEEM
Site Lightings/ Exterior lighting | 26-1 | DEEM | Glenn | Brennan Rhoades | 7657480973 | brhoades@deemfirst.com |  | 60 | 2025-10-30 |  |  | In stock | In stock
2nd Floor Interior Lighting | 26-2 | DEEM | Glenn | Brennan Rhoades | 7657480973 | brhoades@deemfirst.com |  | Sent Email 05/28/2025 | 2025-10-28 |  |  | In stock | In stock
1st Floor Interior Lighting |  |  | Glenn | Brennan Rhoades | (765) 748-0973 | brhoades@deemfirst.com |  | Sent Email 05/28/2025 | 2025-12-04 |  |  | In stock | In stock
Transformer |  |  | Andrew | Brennan Rhoades | (765) 748-0973 | brhoades@deemfirst.com |  | Sent Email 10/6/2025 | 2025-10-17 |  |  |  | 2025-11-04 |  | Robert & Alex with DEEM are to provide an update
Big A$$ Fans |  |  | Glenn | Waiting on Glenn | Waiting on Glenn | Waiting on Glen |  | Tbd | 2025-10-13 |  |  |  | 2025-10-09
Justin Dorsey
2nd Floor Plumbing Fixtures and Fittings | 22-1 | Justin Dorsey | Glenn | Tom Tinkle | (317) 751-2590 | Tom@justindorseyplumbing.com |  | 3 days (Stock Items) | 2025-10-08 |  | 2025-05-05 |  | 2025-10-08
1st Floor Plumbing and Fittings | 22-1 | Justin Dorsey | Glenn | Tom Tinkle | (317) 751-2590 | Tom@justindorseyplumbing.com |  | 3 days (Stock Items) |  |  |  |  | 2025-10-08
Diamond Glass
Glass | 08-1 | Diamond Glass | Glenn | David Driscoll | 317-951-4700 | driscoll@diamondglassworks.net |  | 15 | 2025-10-13 | not complete | not complete | not complete |  | 2025-10-06 | will have to order new glass due to field differences
Storefront | 08-2 | Diamond Glass | Glenn | David Driscoll | 317-951-4700 | driscoll@diamondglassworks.net |  | 25 | 2025-10-13 | not complete | not complete | not complete |  | 2025-10-06 | Arrived at Diamond Glasses shop
Executive Elevator
Elevator Equip |  | Executive Elevator |  | JW Moore | (317) 696-0471 | jwm@exelevator.com |  | 14 (weeks) | 2025-10-13 | 2025-04-18 | 2025-04-23 | 2025-05-29 | Week of 10/6-10/10 | 2025-10-06 | Arrived at Executive Elevators shop
Merritt Contracting
Bollards | 05-7 | Alleato Group | Chad | Chad Tragesser | 765-480-0703 | ctragesser@alleatogroup.com | 4 | 0 | 2025-06-27 |  |  |  | installed
True Step
Interior Stairs | 05-4 | True Step | Andrew | Tim Sutter | (513) 600-7392 | tims@truestepllc.com | 3 | 45 | 2025-10-08 |  |  |  | 2025-09-01 | 2025-10-08
Exterior Stairs |  | True Step | Andrew | Tim Sutter | (513) 600-7392 | tims@truestepllc.com |  |  | TBD |  |  |  | 2025-10-03 | 2025-10-08
Railing
Awning Partners
Metal Awning | 05-6 | Awning Partners | Andrew | Kyle Shelton | (317) 614-0584 | kyle@awningpartners.com | 1 | 60 | 2025-10-27 | 2025-04-16 | 2025-04-24 | 2025-04-24 | 2025-10-27 |  | Follow up on 7/1/2025 that awnings are in Fab.
Professional Garage Door Systems, Inc.
OH Doors | 08-3 | Professional Garage Door Systems, Inc. | Andrew | David Biddle | 3178393050 | Dbiddle@ProDoorSystems.com |  | 5-6 weeks | 2025-09-30 | 2025-05-07 |  |  | 2025-09-30 |  | 07/10, released but not ordered yet. Need door submittal (Glenn notified on 07/10)
Counter Shutters |  | Professional Garage Door Systems, Inc. | Andrew | David Biddle | (317) 839-3050 | Dbiddle@ProDoorSystems.com |  | 5-6 weeks
North Indy Fence Deck & Rail
Enclosure Gates | 05-09 | North Indy Fence Deck & Rail | Glenn | Bob Ray | (317) 848-8814 | bob@northindyfence.com | 2 | 1 week | 2025-11-10 |  |  |  | 2025-10-17 |  | Spoke to Bob Ray on 10/08/2025
Gate Posts | N/A | North Indy Fence Deck & Rail | Glenn | Bob Ray | (317) 848-8814 | bob@northindyfence.com | 3 | in stock | 2025-06-26 |  |  | 2025-06-18 | 2025-06-26 | 2025-07-03 | installed
Damn Good Interiors
2nd Floor Furniture/ Seating | 12-6 | FG Schaefer Co | Glenn | Daniel Stewart | (513) 254-4525 | dstewart@fgschaefer.com |  | Sent Email 05/28/2025 | 2025-11-14 |  |  | 2025-09-01 | Waiting for update from Daniel
1st Floor Furniture/Seating |  | FG Schaefer Co | Glenn | Daniel Stewart | (513) 254-4525 | dstewart@fgschaefer.com |  | Sent Email 05/28/2025 | 2026-01-07 |  |  | 2025-09-01 | Waiting for update from Daniel
2nd Floor Exterior Patio Furniture/ Seating | 12-7 | FG Schaefer Co | Glenn | Daniel Stewart | (513) 254-4525 | dstewart@fgschaefer.com |  | Sent Email 05/28/2025 | 2025-10-06 |  |  | 2025-09-01 | Waiting for update from Daniel
1st Floor Exterior Patio Furniture/ Seating | 12-7 | FG Schaefer Co | Glenn | Daniel Stewart | (513) 254-4525 | dstewart@fgschaefer.com |  | Sent Email 05/28/2025 | 2025-10-06 |  |  | 2025-09-01 | Waiting for update from Daniel
CIH
Exterior Doors | 08-04 | CIH | Andrew | Vivian Husband | 317-498-2593 | husbandv@cih-inc.com |  | 7 weeks | 2025-10-10 | 2025-08-18 | 2025-08-25 | 2025-08-25 | 2025-10-23 |  | Will have delivery date by 10/10
Exterior Frames | 08-04 | CIH | Andrew | Vivian Husband | 317-498-2593 | husbandv@cih-inc.com |  | 12 weeks | 2025-11-21 | 2025-08-18 | 2025-08-25 | 2025-08-25 | 2025-10-16 |  | In Stock
Exterior Door Hardware | 08-04 | CIH | Andrew | Vivian Husband | 317-498-2593 | husbandv@cih-inc.com |  | 10 weeks | 2025-11-21 | 2025-08-18 | 2025-08-25 | 2025-08-25 | 2025-10-23 |  | Will have delivery date by 10/10
Interior Frames | 08-04 | CIH | Andrew | Vivian Husband | 317-498-2593 | husbandv@cih-inc.com |  |  |  |  | 2025-08-25 | 2025-08-25 | 2025-10-23
Interior Doors & Hardware |  |  | Andrew | Vivian Husband | 317-498-2593 | husbandv@cih-inc.com |  |  |  |  | 2025-08-25 | 2025-08-25 | 2025-10-30
Div-10 | 10-1 | CIH | Andrew | Mandi Boyer | (317) 914-7323 | boyera@cih-inc.com |  | In stock |  |  |  | In stock | 2025-11-20
Bathroom Partitions |  | CIH | Andrew | Mandi Boyer | (317) 914-7323 | boyera@cih-inc.com |  | 4 weeks | 2025-11-20 |  |  | TBD | 2025-11-24
Superior
Studs | 09-1 | Superior | Glenn | Brian Jones | (317) 354-0460 | BrianJ@indysuperior.com |  | In Stock | 2025-09-29 |  |  |  |  | On Site
Drywall | 09-4 | Superior | Glenn | Brian Jones | (317) 354-0460 | BrianJ@indysuperior.com |  | In Stock | 2025-11-05 |  |  |  |  | andrew will confirm with Aaron on 10/8
1st & 2nd Floor ACT Tile | 09-3 | Superior | Glenn | Brian Jones | (317) 354-0460 | BrianJ@indysuperior.com |  | In Stock | 2025-11-26 |  |  |  |  | andrew will confirm with Aaron on 10/8
VB ACT Tile | 09-3 | Superior | Glenn | Brain Jones | (317) 354-0460 | BrianJ@indysuperior.com |  | In Stock | 2025-10-06 |  |  |  |  | andrew will confirm with Aaron on 10/8
Unknown
Mechanical Screen |  | Unkown | [6 empty] | 2025-08-07
| 08-6 | Unkown | [6 empty] | 2025-09-25
| 09-3 | Unkown | [6 empty] | 2025-10-21
| 09-3 | Unkown | [6 empty] | 2025-11-18
Bathroom Tile | 09-7 | Unkown | [6 empty] | 10/28 Level 1 12/2/2025 Level 2
Wine/Coffee Bar Tile | 09-7.1 | Unkown
Ice Cream Tile | 09-7.2 | Unkown
Bathroom Accessories | 10-2 | Unkown
Interior Signage | 10-3 | Unkown
Bike Rack | 10-5 | Amazon | Chad | install Merritt | 765-480-0703 | ctragesser@alleatogroup.com | 1 | 7 | 2025-09-09 | 2025-06-20 | 2025-06-20 |  | Waiting for update from install
Volleyball Post Sleeves |  | Unkown | Bart | Bart Conners | 317-753-2899 |  | 8 |  | 2025-09-29 |  |  |  | Waiting for update from Bart
Track light 47
Antler 17
Jelly smoke 22
OP-0Illuminate vintage cumstom 5