## Sheet1
Report Type: Action Item
Project: 24-115 Westfield Collective
Status | Priority | Item Number | Title | Assigned To | Due Date
Assigned | Low | 001 | Fix storefront door and strike | Diamond Glassworks and Aluminum Systems | 02/06/2026
Assigned | Low | 002 | paint touch up | S&M Painting | 02/05/2026
Assigned | Low | 003 | cove base | Market Ready Interiors Inc | 02/09/2026
Assigned | Low | 004 | paint touch up | S&M Painting | 02/10/2026
Assigned | Low | 005 | paint runs | S&M Painting
Assigned | Low | 006 | drywall touch up | Superior Contractors
Assigned | Low | 007 | touch paint | S&M Painting
Assigned | Low | 008 | paint runs | S&M Painting
Assigned | Low | 009 | drywall touch up | Superior Contractors
Assigned | Low | 010 | drywall touch up | Superior Contractors
Assigned | Low | 011 | door dings | S&M Painting
Assigned | Low | 012 | install device | Deem, LLC
Assigned | Low | 013 | paint touch up | S&M Painting