## Sheet1
Report Type: Change Request
Project: 24-115 Westfield Collective
Title Number | Contract | Scope | Status | Cost | Revenue | Markup | Tax | Total | Over/Under
CR-2403-0025 R15 ISO at Foundation Perimeter | PC-2403-0001 | Internal | Void | 4304 | 0 | 0 | 0 | 0 | -4304
CR-2403-0028 Mechanical Screens | PC-2403-0001 | Owner Change | Approved | 0 | 0 | 0 | 0 | 0 | 0
CR-2403-0023 Additional Surveying | PC-2403-0001 | Owner Change | Approved | 1650 | 2500 | 284 | 0 | 2784 | 1134
CR-2403-0024 Lime Stabilization | PC-2403-0001 | Owner Change | Void | 80438 | 80438 | 9150 | 0 | 89587 | 9150
CR-2403-0026 DGI Interior Design Additions | PC-2403-0001 | Owner Change | Approved | 682752 | 759500 | 86393 | 0 | 845893 | 163141
CR-2403-0046 FO Box Relocation | PC-2403-0001 | Internal | Approved | 29334 | 0 | 0 | 0 | 0 | -29334
CR-2403-0096 True Step: Canceled CO #1 Partitions: Detailing Charge Only | PC-2403-0001 | Internal | Draft | 578 | 0 | 0 | 0 | 0 | -578
CR-2403-0018 Damn Good Interiors Design | PC-2403-0001 | Owner Change | Approved | 16066 | 8032 | 914 | 0 | 8946 | -7120
CR-2403-0004 Vacation and Reconstruction of Existing Drain Tile | PC-2403-0001 | Owner Change | Approved | 15723 | 15723 | 1788 | 0 | 17511 | 1788
CR-2403-0002 Secondary Plat Services | PC-2403-0001 | Owner Change | Approved | 3500 | 3500 | 398 | 0 | 3898 | 398
CR-2403-0015 United Excavating T&M Tickets | PC-2403-0001 | Owner Change | Approved | 19612 | 15723 | 1788 | 0 | 17511 | -2101
CR-2403-0016 Elevator Equipment Room Relocation | PC-2403-0001 | Internal | Approved | 2260 | 0 | 0 | 0 | 0 | -2260
CR-2403-0012 Add Structure 612 | PC-2403-0001 | Internal | Approved | 3932 | 0 | 0 | 0 | 0 | -3932
CR-2403-0005 Removal of Additional Concrete Foundations | PC-2403-0001 | Internal | Approved | 3889 | 0 | 0 | 0 | 0 | -3889
CR-2403-0019 Center Point Energy Encroachment Application | PC-2403-0001 | Owner Change | Approved | 1300 | 1300 | 148 | 0 | 1448 | 148
CR-2403-0008 Add Kitchen Design and Buildout | PC-2403-0001 | Owner Change | Approved | 303365 | 303365 | 34508 | 0 | 337873 | 34508
CR-2403-0006 ROW Scope Increase From City | PC-2403-0001 | Owner Change | Approved | 10856 | 20856 | 2372 | 0 | 23228 | 12372
CR-2403-0010 Deduct To Split Buildings | PC-2403-0001 | Owner Change | Approved | -1600000 | -1600000 | -182000 | 0 | -1782000 | -182000
CR-2403-0007 Site Work Adds From City Review | PC-2403-0001 | Owner Change | Approved | 15349 | 21349 | 2428 | 0 | 23777 | 8428
CR-2403-0047 Site Work Contingencies | PC-2403-0001 | Owner Change | Approved | 0 | 0 | 0 | 0 | 0 | 0
CR-2403-0021 Trail Pavement Section Credit | PC-2403-0001 | Internal | Approved | -3321 | 0 | 0 | 0 | 0 | 3321
CR-2403-0020 IBeach Logistics Adds | PC-2403-0004 | Owner Change | Approved | 2378 | 2378 | 271 | 0 | 2649 | 271
CR-2403-0027 Awning Deduct | PC-2403-0001 | Internal | Approved | -5460 | 0 | 0 | 0 | 0 | 5460
CR-2403-0032 Add Volley Ball Court Bathrooms | PC-2403-0004 | Owner Change | Approved | 89913 | 93443 | 10629 | 0 | 104072 | 14159
CR-2403-0030 Foundation Fast Cure Mix | PC-2403-0001 | Internal | Void | 6265 | 0 | 0 | 0 | 0 | -6265
CR-2403-0031 Merritt- Additional Stone | PC-2403-0001 | Internal | Approved | 7286 | 0 | 0 | 0 | 0 | -7286
CR-2403-0033 Concrete in VB Courts | PC-2403-0004 | Owner Change | Approved | 48016 | 50000 | 5688 | 0 | 55688 | 7672
CR-2403-0034 VB Spoils Export | PC-2403-0004 | Internal | Approved | 23579 | 0 | 0 | 0 | 0 | -23579
CR-2403-0106 Casework Concepts Deducts | PC-2403-0001 | Internal | Approved | -9728 | 0 | 0 | 0 | 0 | 9728
CR-2403-0036 Deduct For Trailer Power Reconnection | PC-2403-0001 | Internal | Approved | -1545 | 0 | 0 | 0 | 0 | 1545
CR-2403-0037 OH Doors Deduct | PC-2403-0001 | Internal | Approved | -2532 | 0 | 0 | 0 | 0 | 2532
CR-2403-0038 Electrical Design Shortages | PC-2403-0001 | Internal | Approved | 34150 | 0 | 0 | 0 | 0 | -34150
CR-2403-0039 Added Stone For Drive and Crane Pad for Agg Piers | PC-2403-0001 | Internal | Approved | 20160 | 0 | 0 | 0 | 0 | -20160
CR-2403-0040 Concrete Patio Addition | PC-2403-0004 | Owner Change | Approved | 63037 | 72500 | 8247 | 0 | 80747 | 17710
CR-2403-0041 Concrete Contingency | PC-2403-0001 | Owner Change | Approved | 10569 | 0 | 0 | 0 | 0 | -10569
CR-2403-0003 Permits and Inspections | PC-2403-0001 | Owner Change | Approved | 37897 | 37897 | 4311 | 0 | 42208 | 4311
CR-2403-0044 LeMaster Items Left Off Subcontract | PC-2403-0001 | Internal | Approved | 103500 | 0 | 0 | 0 | 0 | -103500
CR-2403-0043 Perimeter Trail Deduct From DPW | PC-2403-0001 | Internal | Approved | -34692 | 0 | 0 | 0 | 0 | 34692
CR-2403-0098 True Step CO #7 Rail Post Design Change | PC-2403-0001 | Internal | Approved | 26880 | 0 | 0 | 0 | 0 | -26880
CR-2403-0042 HVAC Deduct to FITE | PC-2403-0001 | Internal | Approved | -201000 | 0 | 0 | 0 | 0 | 201000
CR-2403-0099 Euro Plastering Winter Conditions | PC-2403-0001 | Internal | Approved | 5000 | 0 | 0 | 0 | 0 | -5000
CR-2403-0045 Big Ass Fans | PC-2403-0004 | Internal | Approved | 25854 | 0 | 0 | 0 | 0 | -25854
CR-2403-0108 8 Added Feminine Hygiene Waste Baskets | PC-2403-0001 | Internal | Approved | 353 | 0 | 0 | 0 | 0 | -353
CR-2403-0100 Remove and Reinstall Windows and Store Fronts due to vapor barrier | PC-2403-0001 | Internal | Approved | 4850 | 0 | 0 | 0 | 0 | -4850
CR-2403-0051 Tracked Equipment Rental | PC-2403-0001 | Internal | Approved | 3623 | 0 | 0 | 0 | 0 | -3623
CR-2403-0101 S&M Painting, painting all MEPs in ceiling, dryfall paint, add for painting sound spray | PC-2403-0001 | Internal | Approved | 21692 | 0 | 0 | 0 | 0 | -21692
CR-2403-0050 Access Panels At Beer Wall | PC-2403-0001 | Owner Change | Approved | 1650 | 2500 | 284 | 0 | 2784 | 1134
CR-2403-0102 Added Piping for new kitchen & Updated Beer Chase | PC-2403-0001 | Owner Change | Draft | 23018 | 23018 | 2618 | 0 | 25636 | 2618
CR-2403-0109 Sand and Seal Vendor Kitchens, Bars, Ice Cream Shop, and Commissary | PC-2403-0001 | Owner Change | Rejected | 17800 | 17800 | 2025 | 0 | 19825 | 2025
CR-2403-0118 S&M CO #5, painting SSB trim, | PC-2403-0001 | Internal | Draft | 2250 | 0 | 0 | 0 | 0 | -2250
CR-2403-0103 SSB Added Install Labor | PC-2403-0001 | Internal | Void | 1900 | 0 | 0 | 0 | 0 | -1900
CR-2403-0117 Added HVAC work in Elevator Mechanical Room | PC-2403-0001 | Internal | Approved | 2630 | 0 | 0 | 0 | 0 | -2630
CR-2403-0104 LeMaster December Extra Labor Costs | PC-2403-0001 | Internal | Draft | 200 | 0 | 0 | 0 | 0 | -200
CR-2403-0110 DGI Design Change: Coffee/ Bourbon Bar | PC-2403-0001 | Owner Change | Approved | 955 | 955 | 109 | 0 | 1064 | 109
CR-2403-0114 2nd Floor Patio wood board extension | PC-2403-0001 | Owner Change | Rejected | 14261 | 16711 | 1901 | 0 | 18612 | 4351
CR-2403-0105 LeMaster January Extra Labor Costs | PC-2403-0001 | Internal | Approved | 2914 | 0 | 0 | 0 | 0 | -2914
CR-2403-0052 Added Downspouts and Underdrains | PC-2403-0001 | Internal | Approved | 5720 | 0 | 0 | 0 | 0 | -5720
CR-2403-0048 ROW Undercutting | PC-2403-0001 | Internal | In Review | 24050 | 0 | 0 | 0 | 0 | -24050
CR-2403-0053 Re-Prep SOG | PC-2403-0001 | Internal | Approved | 16500 | 0 | 0 | 0 | 0 | -16500
CR-2403-0054 Fiber Optic Box Relocation | PC-2403-0001 | Owner Change | Approved | 29334 | 29334 | 3337 | 0 | 32670 | 3337
CR-2403-0107 Added Booster for Dishwasher | PC-2403-0001 | Owner Change | Rejected | 5299 | 5799 | 660 | 0 | 6458 | 1160
CR-2403-0055 Final Permit and Inspection Fees | PC-2403-0001 | Owner Change | Draft | 1882 | 1882 | 214 | 0 | 2096 | 214
CR-2403-0056 November Design Adds | PC-2403-0001 | Owner Change | Approved | 208483 | 233390 | 26548 | 0 | 259938 | 51455
CR-2403-0057 December Design Adds | PC-2403-0001 | Owner Change | Approved | 223523 | 247500 | 28153 | 0 | 275653 | 52130
CR-2403-0059 RTU Curb Reinforcement for Screens | PC-2403-0001 | Internal | Approved | 17610 | 0 | 0 | 0 | 0 | -17610
CR-2403-0060 LeMaster Tickets | PC-2403-0001 | Internal | Approved | 1783 | 0 | 0 | 0 | 0 | -1783
CR-2403-0061 Added Commissary Access door EX111A | PC-2403-0001 | Owner Change | Approved | 2852 | 3402 | 387 | 0 | 3789 | 937
CR-2403-0062 Overtime work | PC-2403-0001 | Internal | Approved | 1320 | 0 | 0 | 0 | 0 | -1320
CR-2403-0063 Deduct ceramic Floor tile around bar 1st and 2nd floor | PC-2403-0001 | Owner Change | Approved | -7200 | -7200 | -819 | 0 | -8019 | -819
CR-2403-0064 Deduct storefront windows from 6'4" to 6'0" | PC-2403-0001 | Internal | Draft | 1915 | 0 | 0 | 0 | 0 | -1915
CR-2403-0065 Demo Curb Walk Combo at Dumpster | PC-2403-0001 | Internal | Draft | 2270 | 0 | 0 | 0 | 0 | -2270
CR-2403-0066 HVAC Design Change after site walk with Brandon | PC-2403-0001 | Internal | Draft | 23650 | 0 | 0 | 0 | 0 | -23650
CR-2403-0075 Ceiling tile VE option credit and Frame between existing building girts and tyvek in two areas | PC-2403-0001 | Internal | Draft | -4080 | 0 | 0 | 0 | 0 | 4080
CR-2403-0077 Monument Sign Deduct | PC-2403-0001 | Owner Change | Approved | -1646 | -1646 | -187 | 0 | -1833 | -187
CR-2403-0089 Cut Down Frames on 2nd Floor West Elevation | PC-2403-0001 | Internal | Approved | 3185 | 0 | 0 | 0 | 0 | -3185
CR-2403-0078 Added sidewalk from North volleyball patio to dumpster sidewalk | PC-2403-0001 | Owner Change | Approved | 1650 | 1650 | 188 | 0 | 1838 | 188
CR-2403-0074 Superior had to cut the frame to the riser room. Superior to install all exterior hollow metal doors, frames, and hardware | PC-2403-0001 | Internal | Approved | 3125 | 0 | 0 | 0 | 0 | -3125
CR-2403-0076 Elevator Equipment Room, New Wall outside Private Room, Install 5 welded window frames | PC-2403-0001 | Internal | Draft | 3272 | 0 | 0 | 0 | 0 | -3272
CR-2403-0069 DGI 10.28.25 Updated Interior Design | PC-2403-0001 | Owner Change | Approved | 20275 | 20275 | 2306 | 0 | 22581 | 2306
CR-2403-0067 (Craving Crapes) Added sidewalk from North volleyball patio to dumpster sidewalk | PC-2403-0004 | Owner Change | Approved | 1652 | 1652 | 188 | 0 | 1840 | 188
CR-2403-0083 Brake Metal trim at single doors | PC-2403-0001 | Internal | Approved | 285 | 0 | 0 | 0 | 0 | -285
CR-2403-0079 (3) Added Exterior Gooseneck Light | PC-2403-0001 | Owner Change | Approved | 2500 | 2500 | 284 | 0 | 2784 | 284
CR-2403-0070 CMU Block wall tear down at main entrance | PC-2403-0001 | Internal | Approved | 10400 | 0 | 0 | 0 | 0 | -10400
CR-2403-0068 Replace Damaged Frame 123 (DKM) | PC-2403-0004 | Internal | Approved | 0 | 0 | 0 | 0 | 0 | 0
CR-2403-0082 Kebony Cladding Board | PC-2403-0001 | Internal | Draft | 8336 | 0 | 0 | 0 | 0 | -8336
CR-2403-0080 11/12/2025 Owner Site Walk Add | PC-2403-0001 | Owner Change | Approved | 5324 | 5324 | 606 | 0 | 5930 | 606
CR-2403-0081 11.20.2025 Interior Design Updates (2nd Lvl Beer Wall) | PC-2403-0001 | Owner Change | Approved | 18881 | 22531 | 2563 | 0 | 25094 | 6213
CR-2403-0084 East Interior Volleyball wall fur out | PC-2403-0004 | Owner Change | Rejected | 14433 | 14433 | 1642 | 0 | 16075 | 1642
CR-2403-0085 Deduct for drink rails and high tops | PC-2403-0001 | Internal | Draft | -58771 | 0 | 0 | 0 | 0 | 58771
CR-2403-0086 Added interior walking path along the South and East perimeter of the volleyball building | PC-2403-0004 | Owner Change | Rejected | 23005 | 33005 | 3754 | 0 | 36759 | 13754
CR-2403-0088 Remove and reinstall storefront for vapor barrier installation | PC-2403-0001 | Internal | Void | 0 | 0 | 0 | 0 | 0 | 0
CR-2403-0087 Winter Conditions (Merritt) | PC-2403-0001 | Internal | Approved | 688 | 0 | 0 | 0 | 0 | -688
CR-2403-0111 DEEM Electrical Change Orders | PC-2403-0001 | Owner Change | Draft | 5084 | 5084 | 578 | 0 | 5662 | 578
CR-2403-0090 Fire Rated Ceiling in Elevator Mech Room | PC-2403-0001 | Internal | Approved | 490 | 0 | 0 | 0 | 0 | -490
CR-2403-0091 Commissary Bulkhead & hard lid | PC-2403-0001 | Internal | Approved | 1898 | 0 | 0 | 0 | 0 | -1898
CR-2403-0092 Deduct for FRP locations & Construct 2nd floor window sills (South Wall) | PC-2403-0001 | Internal | Approved | -6800 | 0 | 0 | 0 | 0 | 6800
CR-2403-0093 Elevator Mech Room Door , Frame, Hardware (CIH) | PC-2403-0001 | Internal | Approved | 2605 | 0 | 0 | 0 | 0 | -2605
CR-2403-0094 Added Storage room under interior stair case | PC-2403-0001 | Owner Change | Approved | 6543 | 0 | 0 | 0 | 0 | -6543
CR-2403-0119 Mural Art | PC-2403-0001 | Owner Change | Approved | 16890 | 16890 | 1921 | 0 | 18811 | 1921
CR-2403-0115 Painting 1st and 2nd floor RR entryways | PC-2403-0001 | Owner Change | Approved | 1750 | 2400 | 273 | 0 | 2673 | 923
CR-2403-0116 2nd Floor Casework (C-04) booth safety caps | PC-2403-0001 | Owner Change | Approved | 1640 | 2200 | 250 | 0 | 2450 | 810
CR-2403-0112 1st and 2nd floor bar islands | PC-2403-0001 | Owner Change | Approved | 13088 | 15120 | 1720 | 0 | 16840 | 3752
CR-2403-0113 Ice Cream Shop (4) Added Receptacles | PC-2403-0001 | Owner Change | Approved | 6035 | 6635 | 755 | 0 | 7390 | 1355
CR-2403-0095 Men's and Women's Bath Accessories | PC-2403-0001 | Internal | Approved | 3546 | 0 | 0 | 0 | 0 | -3546
CR-2403-0120 Refurbish (2) Owner Provided Countertops | PC-2403-0001 | Owner Change | Approved | 600 | 600 | 68 | 0 | 668 | 68
CR-2403-0121 (2) Two Semi Recessed Trash Units | PC-2403-0001 | Owner Change | Approved | 1494 | 1494 | 170 | 0 | 1664 | 170
CR-2403-0122 Install electrical cover plates at all owner provided lighting locations to prevent schedule delays | PC-2403-0001 | Owner Change | Approved | 1075 | 1075 | 122 | 0 | 1197 | 122
CR-2403-0123 Lost & Damaged Items (CIH) | PC-2403-0001 | Internal | Draft | 0 | 0 | 0 | 0 | 0 | 0
CR-2403-0124 Additional Kebony Boards needed to complete North patio stairs | PC-2403-0001 | Internal | Approved | 3557 | 0 | 0 | 0 | 0 | -3557
CR-2403-0125 Changing Opening 123 from a 20min fire rating to a 45 min. fire rating | PC-2403-0001 | Internal | Approved | 2648 | 0 | 0 | 0 | 0 | -2648
|  |  |  | 612854.89 | 614813.83 | 69935.3 | 0 | 684749.13 | 71894.24