## Sheet1
Report Type: Punch List
Project: 24-115 Westfield Collective
Status | Priority | Item Number | Title | Assigned To | Due Date
Work Completed | Critical | 001 | Vendor space E | Justin Dorsey Plumbing | 02/02/2026
Work Completed | Medium | 002 | Elevator Install | Executive Elevator Company | 02/06/2026
Work Completed | Low | 003 | Drywall Touch up | Superior Contractors | 02/06/2026
Work Completed | Low | 004 | Bathroom partitions | Superior Contractors | 02/06/2026
Work Completed | Low | 005 | Counter top install | Marble Uniques | 02/05/2026
Work Completed | Low | 006 | Install toilet and urinal | Justin Dorsey Plumbing | 02/06/2026
Work Completed | Medium | 007 | Install faucets | Justin Dorsey Plumbing | 02/09/2026
Not Resolved | Medium | 008 | Touch up paint | S&M Painting | 02/26/2026
Work Completed | Medium | 009 | Install Floor mount toilet | Justin Dorsey Plumbing | 02/06/2026
Work Completed | Medium | 010 | Drywall touch up | Superior Contractors | 02/06/2026
Work Completed | Medium | 011 | Counter top install | Marble Uniques | 02/06/2026
Work Completed | Medium | 012 | Fire device | Deem, LLC | 02/09/2026
Work Completed | Medium | 013 | Faucet install | Justin Dorsey Plumbing | 02/09/2026
Work Completed | Medium | 014 | Replace ACT tile | Vulcn | 02/18/2026
Work Completed | High | 015 | Touch up paint | S&M Painting | 02/27/2026
Work Completed | Medium | 016 | Bathroom accessories | Superior Contractors | 02/12/2026
Work Completed | Low | 017 | Cove base install | Market Ready Interiors Inc | 02/11/2026
Work Completed | Low | 018 | Drywall touch up | Superior Contractors | 02/10/2026
Work Completed | High | 019 | 2nd floor beer wall | Alleato Group | 02/25/2026
Work Completed | Medium | 020 | Finish tile and grout second floor beer wall. | Market Ready Interiors Inc | 02/11/2026
Work Completed | Medium | 021 | Install ACT Pads | Superior Contractors | 02/12/2026
Work Completed | Medium | 022 | Patch Electrical holes | Deem, LLC | 02/06/2026
Work Completed | Medium | 023 | Panic bar 111A | Superior Contractors | 02/06/2026
Work Completed | Medium | 024 | Cover plates | Deem, LLC | 02/06/2026
Work Completed | Medium | 025 | Pour concrete back | Justin Dorsey Plumbing | 02/06/2026
Work Completed | Medium | 026 | Fire alarm devices | Deem, LLC | 02/09/2026
Work Completed | Medium | 027 | Install cove base. | Market Ready Interiors Inc | 02/10/2026
Work Completed | Medium | 028 | Install fire alarm device. | Deem, LLC | 02/09/2026
Work Completed | Medium | 029 | Install 2x2' light. | Deem, LLC | 02/06/2026
Work Completed | High | 030 | Mop sink install | Justin Dorsey Plumbing | 02/09/2026
Work Completed | Low | 031 | Install a strap on flex duct work in the ceiling | C&S Heating & Cooling Inc. | 02/04/2026
Work Completed | Medium | 032 | Elynson door install | Superior Contractors | 02/10/2026
Not Resolved | High | 033 | 2nd floor bar rope lighting | Deem, LLC | 03/03/2026
Assigned | Medium | 034 | 2nd floor bar equipment | FG Schaefer Co | 02/27/2026
Work Completed | Medium | 035 | Fan controls | Deem, LLC | 02/09/2026
Work Completed | Medium | 036 | Finish installing ACT Pads | Superior Contractors | 02/06/2026
Work Completed | Medium | 037 | Touch up SSB | S&M Painting | 02/11/2026
Work Completed | Medium | 038 | Install cove base. | Market Ready Interiors Inc | 02/09/2026
Work Completed | Medium | 040 | Cove base | Market Ready Interiors Inc | 02/11/2026
Work Completed | Medium | 041 | Touch up paint at 2nd floor bar | S&M Painting | 02/10/2026
Work Completed | Low | 042 | Touch up paint spots in commissary area | S&M Painting | 02/10/2026
Work Completed | Medium | 043 | Drywall touch up | Superior Contractors | 02/10/2026
Work Completed | Medium | 044 | Relocate exit sign | Deem, LLC | 02/10/2026
Work Completed | Medium | 045 | Finish Tile | Market Ready Interiors Inc | 02/13/2026
Work Completed | Medium | 046 | Casework | Casework Concepts LLC | 02/10/2026
Work Completed | Medium | 047 | Data | Tri-State AV | 02/11/2026
Work Completed | Medium | 048 | Casework and electrical hookup | Casework Concepts LLC | 02/13/2026
Work Completed | Medium | 049 | Cove base | Market Ready Interiors Inc | 02/10/2026
Work Completed | Medium | 050 | Install air curtains | C&S Heating & Cooling Inc. | 02/03/2026
Work Completed | Medium | 051 | Caulking | Caulking Specialists | 02/09/2026
Work Completed | Medium | 052 | Shelves | Casework Concepts LLC | 02/12/2026
Work Completed | Low | 054 | Install toe kicks | Casework Concepts LLC | 02/06/2026
Work Completed | Medium | 055 | Switch device | Deem, LLC | 02/10/2026
Work Completed | Medium | 056 | Touch up SSB | S&M Painting | 02/13/2026
Work Completed | Medium | 057 | Flooring and cove | Market Ready Interiors Inc | 02/12/2026
Work Completed | Medium | 058 | TV install | Tri-State AV | 02/12/2026
Work Completed | Medium | 059 | Finish out data | Tri-State AV | 02/13/2026
Work Completed | Medium | 060 | Touch up | S&M Painting | 02/11/2026
Work Completed | Medium | 061 | Finish cove base installation | Market Ready Interiors Inc | 02/06/2026
Work Completed | Medium | 062 | Cove base | Market Ready Interiors Inc | 02/10/2026
Work Completed | Medium | 063 | Fill in return in dining area | Superior Contractors | 02/06/2026
Work Completed | Medium | 064 | Fire Place and TV | Tri-State AV | 02/13/2026
Assigned | Medium | 065 | Finish casework | Casework Concepts LLC | 02/26/2026
Work Completed | Medium | 066 | Touch up | S&M Painting | 02/12/2026
Work Completed | Medium | 068 | Case work | Casework Concepts LLC | 02/26/2026
Work Completed | Low | 069 | Drywall patch and paint | Superior Contractors | 02/26/2026
Work Completed | Medium | 070 | Touch up paint on ssb | S&M Painting | 02/12/2026
Work Completed | Medium | 071 | Bar equipment install hook up | FG Schaefer Co | 02/11/2026
Work Completed | Medium | 072 | Bar lighting | Deem, LLC | 02/11/2026
Work Completed | Medium | 073 | Finish tile | Market Ready Interiors Inc | 02/13/2026
Work Completed | Medium | 074 | paint column | S&M Painting | 02/06/2026
Work Completed | Medium | 075 | Finish installing shiplap siding on wall. | Market Ready Interiors Inc | 02/06/2026
Work Completed | Medium | 076 | Device Plate | Deem, LLC | 02/09/2026
Work Completed | Medium | 077 | ACT Pads | Superior Contractors | 02/05/2026
Work Completed | Medium | 078 | equipment install in creamery area | FG Schaefer Co | 02/27/2026
Work Completed | Low | 080 | Cove base | Market Ready Interiors Inc | 02/10/2026
Work Completed | Medium | 081 | Creamery equip install hook up | Justin Dorsey Plumbing | 02/26/2026
Work Completed | Medium | 082 | Install device | Deem, LLC | 02/10/2026
Work Completed | Medium | 083 | Finish casework and trim | Casework Concepts LLC | 02/10/2026
Work Completed | Medium | 084 | Mini Split | C&S Heating & Cooling Inc. | 02/04/2026
Assigned | Medium | 085 | Fire Caulk | Deem, LLC | 02/26/2026
Work Completed | Medium | 086 | SSB touch up | S&M Painting | 02/06/2026
Work Completed | Medium | 087 | Touch up | S&M Painting | 02/27/2026
Work Completed | Low | 089 | Finish air curtains | C&S Heating & Cooling Inc. | 02/03/2026
Work Completed | Medium | 090 | Cove base | Market Ready Interiors Inc | 02/10/2026
Work Completed | Medium | 091 | Install cove base | Market Ready Interiors Inc | 02/06/2026
Assigned | Medium | 092 | Finish SSB | Market Ready Interiors Inc | 03/06/2026
Work Completed | Medium | 093 | Electrical data devices | Tri-State AV | 02/11/2026
Work Completed | Medium | 094 | Install back counter top | Marble Uniques | 02/12/2026
Work Completed | Low | 095 | Caulking | Caulking Specialists | 02/10/2026
Work Completed | Medium | 096 | Finis touch up paint at bourbon bar. | S&M Painting | 03/06/2026
Work Completed | Low | 097 | Finish installing cove base | Market Ready Interiors Inc | 02/06/2026
Work Completed | Medium | 099 | Finish elevator room | Executive Elevator Company | 02/11/2026
Work Completed | Medium | 101 | Finish drywall touch up and paint | Superior Contractors | 02/06/2026
Work Completed | Medium | 102 | Install vapor barrier in woman's restroom | Alleato Group | 02/13/2026
Work Completed | Medium | 103 | Install insulation in woman's and men's restroom | Alleato Group | 02/11/2026
Work Completed | Medium | 104 | Finish ACT pad installation | Superior Contractors | 02/11/2026
Work Completed | Medium | 105 | Finish partitions in RR volleyball area | Superior Contractors | 02/12/2026
Work Completed | Low | 106 | Finish countertops in bathrooms | Marble Uniques
Work Completed | Medium | 107 | Finish Plumbing | Justin Dorsey Plumbing | 02/11/2026
Assigned | Medium | 108 | Remove light switch | Deem, LLC | 02/27/2026
Work Completed | Low | 109 | Finishing caulking the top of the tile | Caulking Specialists | 02/11/2026
Work Completed | Low | 110 | Caulk floor drain | Justin Dorsey Plumbing | 02/27/2026
Work Completed | Low | 111 | Equip hook up | FG Schaefer Co | 02/12/2026
Work Completed | Medium | 112 | Exact same as A | Caulking Specialists | 02/12/2026
Work Completed | Medium | 113 | Same as A | Caulking Specialists | 02/12/2026
Work Completed | Medium | 114 | Exact same as A | Caulking Specialists | 02/12/2026
Work Completed | Medium | 115 | exact as vendor A | Caulking Specialists | 02/12/2026
Work Completed | Low | 116 | Cover | Deem, LLC | 02/09/2026
Work Completed | Low | 117 | Install Men’s Bathroom Partition’s | Superior Contractors | 02/12/2026
Work Completed | Low | 118 | Act Tiles | Superior Contractors | 02/09/2026
Work Completed | Low | 120 | Act Tiles | Superior Contractors Inc | 02/09/2026
Work Completed | Low | 121 | Calk Drains | Justin Dorsey Plumbing | 02/16/2026
Work Completed | Low | 123 | Partitions Install | Superior Contractors
Resolved | Low | 124 | Finish Sink Install | Alleato Group | 02/26/2026
Work Completed | Low | 125 | Pain Touch Up | S&M Painting
Work Completed | Low | 127 | Toe Kick Missing | Casework Concepts LLC
Work Completed | Medium | 128 | Hole In The Wall (Spectrum) | Alleato Group
Work Completed | Low | 129 | 2nd Floor West Dining | Deem, LLC
Work Completed | High | 130 | Wood Shelf’s | Casework Concepts LLC | 02/11/2026
Work Completed | Low | 131 | Light Install | Deem, LLC | 02/10/2026
Work Completed | Low | 132 | Remove Bags From Lights | Deem, LLC | 02/10/2026
Work Completed | Low | 133 | Drywall Hole | Superior Contractors | 02/26/2026
Work Completed | Low | 134 | Plumbers Tape Around Gas Pipe | Justin Dorsey Plumbing
Work Completed | Medium | 135 | Drywall Over PEMB Support | Superior Contractors Inc | 02/26/2026
Work Completed | Low | 136 | Covers On Junction Boxes | Deem, LLC
Work Completed | Low | 138 | Drywall Square Repair | Deem, LLC | 02/13/2026
Work Completed | Low | 139 | Paint Sprinkler Pipes | S&M Painting | 02/26/2026
Work Completed | Low | 140 | Paint Black Pipe | S&M Painting | 02/18/2026
Assigned | Medium | 141 | Adjust 2nd Floor Bar Counter Supports (not Level) | Marble Uniques | 03/06/2026
Assigned | Low | 142 | Cap Ends On Roll Up Doors | Alleato Group | 03/03/2026
Work Completed | Low | 143 | Counter Top Polish | Marble Uniques | 02/12/2026
Assigned | High | 144 | Core For Pepsi Line | Justin Dorsey Plumbing | 03/02/2026
Work Completed | Low | 145 | Caulk Bottom Of Tile | Caulking Specialists | 02/26/2026
Work Completed | Low | 146 | Spectrum Hole | Alleato Group
Work Completed | High | 147 | Tape Coming Off Ceiling Insulation | Lemaster Steel Erectors Inc. | 02/12/2026
Assigned | Low | 148 | Drywall | Superior Contractors | 02/26/2026
Work Completed | Medium | 150 | Complete Casework 2nd Floor North Seating | Casework Concepts LLC | 02/12/2026
Work Completed | Low | 151 | Clean Tile From Concrete Slurry | Justin Dorsey Plumbing
Assigned | Low | 152 | Clean Off Grout | Market Ready Interiors Inc | 03/06/2026
Work Completed | Low | 153 | Caulk Around All Door Jambs | Caulking Specialists
Assigned | Low | 154 | Sand Drywall. East Dining Hall | Superior Contractors Inc | 02/26/2026
Work Completed | Low | 155 | East Dining Area Adhesive Brackets | Casework Concepts LLC
Assigned | High | 156 | Schluter Strip Not To The Finish Level Of Tile. Stopped Short | Market Ready Interiors Inc | 03/06/2026
Work Completed | Medium | 157 | Replicate Other Case Work In This Area | Casework Concepts LLC | 02/13/2026
Work Completed | Medium | 157 | Replicate Other Case Work In This Area | Casework Concepts LLC | 02/13/2026
Work Completed | Medium | 159 | Replicate Other Case Work In This Area | Casework Concepts LLC | 02/13/2026
Work Completed | Low | 160 | Market Ready Base Trim | Market Ready Interiors Inc | 02/12/2026
Work Completed | Low | 161 | Aluminum On Threash Hold | Alleato Group | 03/06/2026
Work Completed | High | 162 | Add Adhesive For Shelf’s | Casework Concepts LLC
Assigned | Medium | 163 | Replace Broken Kebony Board | Superior Contractors Inc | 02/27/2026
Assigned | Medium | 164 | Complete South Patio Kebony Rail | Superior Contractors Inc | 03/02/2026
Work Completed | High | 165 | Install Elevator Flooring | Alleato Group | 02/13/2026
Assigned | Low | 166 | Repair Drywall | Superior Contractors | 02/26/2026
Work Completed | Medium | 167 | Install Fireplace | Deem, LLC | 02/12/2026
Assigned | Medium | 168 | Complete 2nd Floor Landing Casework By Fireplace Wall | Casework Concepts LLC | 02/26/2026
Assigned | Medium | 169 | Spectrum Wire (Mike) | Alleato Group | 03/06/2026
Assigned | Medium | 170 | West Side Porch Caulking | Caulking Specialists | 02/27/2026
Assigned | Medium | 171 | Outlet 2nd Floor South Patio | Caulking Specialists | 02/26/2026
Assigned | Medium | 172 | West Side Porch Grind Off Screws | Deem, LLC | 02/27/2026
Assigned | Medium | 173 | West Side Porch Grind Off Screws | Deem, LLC | 02/27/2026
Work Completed | High | 174 | Rough In For Lights Men’s 1st And 2nd Floor Bathrooms | Deem, LLC | 02/10/2026
Work Completed | Medium | 175 | 1 X’s | Superior Contractors Inc | 02/12/2026
Assigned | Medium | 176 | Paint Beam | S&M Painting | 02/27/2026
Assigned | Medium | 178 | Remove All Unused Conduits On 2nd Floor Patio | Caulking Specialists | 02/26/2026
Work Completed | Medium | 179 | Polish Counter Edge | Marble Uniques
Work Completed | Medium | 180 | Electrical Box 2nd Floor Patio | Deem, LLC | 02/10/2026
Assigned | Medium | 181 | Paint Touch Up Around Window | EURO Plastering | 02/27/2026
Work Completed | Medium | 182 | Outlet Second Floor Patio | Deem, LLC | 02/13/2026
Work Completed | Medium | 183 | Address Fire Device | Deem, LLC | 02/12/2026
Work Completed | Medium | 184 | North Side Porch Device | Deem, LLC | 02/13/2026
Work Completed | High | 185 | FA Device North 2nd Floor Patio | Deem, LLC | 02/10/2026
Work Completed | Medium | 186 | Secure Post | LeMaster Steel Erectors Inc. | 02/12/2026
Work Completed | Medium | 187 | Secure Post | LeMaster Steel Erectors Inc. | 02/12/2026
Assigned | Medium | 188 | Install 1xs | Superior Contractors | 02/27/2026
Assigned | Medium | 189 | Silicone Gutter | Lemaster Steel Erectors Inc. | 03/06/2026
Work Completed | Medium | 190 | Straighten Wood Patio Rail and install back cap | Superior Contractors Inc | 02/12/2026
Work Completed | High | 191 | Missing FA device | Deem, LLC | 02/13/2026
Assigned | Medium | 192 | AV Boxes Incomplete | Alleato Group | 03/06/2026
Assigned | Medium | 193 | Complete Kebony Wood Handrail | Superior Contractors Inc | 02/27/2026
Work Completed | Medium | 194 | Complete West Staircase Kebony Board | Superior Contractors Inc | 02/10/2026
Assigned | Medium | 195 | Cap Anchor Bolts | Alleato Group | 03/06/2026
Work Completed | Medium | 196 | Address Junction Boxes | Deem, LLC
Work Completed | Medium | 197 | Electrical Wip’s | Deem, LLC | 02/12/2026
Work Completed | Medium | 198 | Electrical Wip’s | Deem, LLC | 02/12/2026
Assigned | Medium | 199 | Base Board On Creamery | Market Ready Interiors Inc | 03/06/2026
Work Completed | Medium | 201 | Drywal finish elevator openings 1st and 2nd floor | Superior Contractors Inc | 02/13/2026
Work Completed | Low | 202 | Sand drywall at 1st and 2nd floor bar | Superior Contractors Inc | 02/16/2026
Assigned | Medium | 203 | Fix drywall outside of volleyball bathrooms | Superior Contractors Inc | 03/02/2026
Assigned | Low | 204 | Drywall Touch Up | S & M Painting and Drywall Co. | 03/06/2026
Work Completed | Medium | 205 | Kitchen | DEEM
Work Completed | Low | 206 | Vendor A Outlets | Nobody
Assigned | High | 208 | West Side Sprinkler System Re-route | Vulcn | 03/06/2026
Not Resolved | High | 209 | Re-route Sprinkler | Vulcn | 03/06/2026
Assigned | High | 210 | Re-route Sprinkler | Vulcn | 03/06/2026
Assigned | High | 211 | Re-route South East fire sprinkler | Vulcn | 02/27/2026
Assigned | Low | 212 | Elevator Threshold | Alleato Group | 03/06/2026
Assigned | Low | 213 | Backer Rod And Caulk Exit door next To Volleyball Bathrooms | Diamond Glassworks and Aluminum Systems | 02/26/2026
Assigned | High | 214 | Paint in Women's volleyball restroom | S&M Painting | 02/27/2026
Work Completed | High | 215 | Install insulation in cavity at north exit door in volleyball (to the east of volleyball bathrooms) | Alleato Group | 02/26/2026
Assigned | High | 216 | Backer rod and caulk North volleyball exit door. (east of volleyball RR) | Diamond Glassworks and Aluminum Systems | 02/26/2026