## Task List - 24-115 Westfield Co
Project Contacts | Project Contacts | Project Contacts | Project Contacts | Project Contacts | Project: 24-115 Westfield Collective
Name | Type | Email | Phone |  | Exported On: Mon 03/02/2026 08:08 PM
Andrew Cannon | Project Engineer | acannon@alleatogroup.com | US
Jesse Dawson | Vice President | jdawson@alleatogroup.com | US
Brandon Clymer | CEO | bclymer@alleatogroup.com | US
Chad Tragesser | Superintendent | ctragesser@alleatogroup.com | US
Glenn Ducharme | Project Manager | gducharme@alleatogroup.com | US
Ty Inman | Assistant Superintendent | tinman@alleatogroup.com | US
Tasks | Tasks | Tasks | Tasks | Tasks | Tasks | Tasks
Task Name | Start Date | Finish Date | Percent Complete | Status | Groups | Assigned To
Receive notice to proceed and sign contract | Mon 02/03/2025 | Mon 02/03/2025 | 0% | Not Started
Prepare and submit project schedule | Mon 02/03/2025 | Mon 02/03/2025 | 0% | Not Started
Complete Structural Design Parameters | Mon 02/03/2025 | Wed 02/05/2025 | 0% | Not Started
Final Architectural Design Drawings | Mon 02/03/2025 | Fri 04/04/2025 | 0% | Not Started
Preconstruction & Design | Mon 02/03/2025 | Fri 05/02/2025 | 0% | Not Started
PEMP Drawings | Wed 02/05/2025 | Tue 04/01/2025 | 0% | Not Started
Fire Sprinkler Design Drawings | Mon 02/17/2025 | Fri 03/14/2025 | 0% | Not Started
Plumbing Design Drawings | Mon 02/17/2025 | Fri 03/14/2025 | 0% | Not Started
Mechanical Design Drawings | Mon 02/17/2025 | Fri 03/14/2025 | 0% | Not Started
Fire Alarm Design Drawings | Mon 02/17/2025 | Fri 03/14/2025 | 0% | Not Started
Electrical Design Drawings | Mon 02/17/2025 | Fri 03/14/2025 | 0% | Not Started
Long Lead Procurement | Mon 02/17/2025 | Fri 06/27/2025 | 0% | Not Started
Structural Design For Permit | Thu 02/20/2025 | Fri 02/21/2025 | 0% | Not Started
Civil Plans for Permit | Fri 02/21/2025 | Mon 02/24/2025 | 0% | Not Started
Submit Site & Structural Foundation Permit | Tue 02/25/2025 | Tue 02/25/2025 | 0% | Not Started
Water Service | Tue 02/25/2025 | Mon 03/10/2025 | 0% | Not Started
Storm Structures | Tue 02/25/2025 | Mon 04/07/2025 | 0% | Not Started
Obtain Site & Structural building permit | Tue 03/11/2025 | Mon 03/31/2025 | 0% | Not Started
Electrical Gear | Mon 03/17/2025 | Fri 05/09/2025 | 0% | Not Started
Light Fixtures | Mon 03/17/2025 | Fri 05/09/2025 | 0% | Not Started
RTUs | Mon 03/17/2025 | Fri 05/09/2025 | 0% | Not Started
Site Grading and Utilities | Tue 03/25/2025 | Wed 10/01/2025 | 0% | Not Started
Install temporary water service/relocate existing if possible | Tue 04/01/2025 | Wed 04/02/2025 | 0% | Not Started
Erosion Control | Tue 04/01/2025 | Thu 04/03/2025 | 100% | Complete
Set line and grade benchmarks | Tue 04/01/2025 | Thu 04/03/2025 | 0% | Not Started
Mobilize on Site | Tue 04/01/2025 | Tue 04/29/2025 | 0% | Not Started
Final Structural Design Drawings | Wed 04/02/2025 | Thu 04/10/2025 | 0% | Not Started
PEMB steel Package | Wed 04/02/2025 | Tue 05/27/2025 | 0% | Not Started
Clear and grub site | Fri 04/04/2025 | Tue 04/08/2025 | 100% | Complete
Millwork | Mon 04/07/2025 | Fri 05/16/2025 | 0% | Not Started
Elevator | Mon 04/07/2025 | Fri 06/27/2025 | 0% | Not Started
Storefront | Mon 04/07/2025 | Fri 06/27/2025 | 0% | Not Started
Remove Existing VB court Fence South Side | Wed 04/09/2025 | Wed 04/09/2025 | 0% | Not Started
Install temporary power/relocate existing if possible | Wed 04/09/2025 | Thu 04/10/2025 | 100% | Complete
Stone site access and temporary parking area | Wed 04/09/2025 | Thu 04/10/2025 | 100% | Complete
Building Permit Submittal | Fri 04/11/2025 | Fri 04/11/2025 | 0% | Not Started
Rough grade site (cut and fill) | Fri 04/11/2025 | Mon 04/14/2025 | 0% | Not Started
Metal Railings | Fri 04/11/2025 | Thu 05/22/2025 | 0% | Not Started
Building Permit Approval | Mon 04/14/2025 | Fri 05/02/2025 | 0% | Not Started
Install Gas Main | Tue 04/15/2025 | Wed 04/16/2025 | 0% | Not Started
Set up site office | Tue 04/15/2025 | Thu 04/17/2025 | 100% | Complete
Install Sanitary Sewer | Tue 04/15/2025 | Mon 04/21/2025 | 0% | Not Started
Install storm drainage | Tue 04/15/2025 | Mon 04/28/2025 | 0% | Not Started
Domestic water & fire line | Tue 04/15/2025 | Mon 04/28/2025 | 0% | Not Started
Foundations | Mon 04/28/2025 | Fri 08/01/2025 | 0% | Not Started
Install Temp Fence & Gates | Tue 04/29/2025 | Tue 04/29/2025 | 100% | Complete
Storm Inlet Protection | Tue 04/29/2025 | Tue 04/29/2025 | 0% | Not Started
Dumpster Enclosure Bollards | Tue 04/29/2025 | Wed 04/30/2025 | 0% | Not Started
Dumpster Gate Posts | Tue 04/29/2025 | Wed 04/30/2025 | 0% | Not Started
Fire hydrants and PIV valve | Tue 04/29/2025 | Thu 05/01/2025 | 0% | Not Started
Site Electrical, Primary Sleeves and Light Pole Bases | Tue 04/29/2025 | Mon 05/05/2025 | 0% | Not Started
Install New VB Court Fence | Tue 04/29/2025 | Mon 05/05/2025 | 0% | Not Started
Dumpster Pad | Thu 05/01/2025 | Mon 05/05/2025 | 0% | Not Started
Flush & Test Water Mains | Fri 05/02/2025 | Tue 05/06/2025 | 0% | Not Started
Monument Sign Foundation | Tue 05/06/2025 | Thu 05/08/2025 | 0% | Not Started
Perform final site grading | Tue 05/06/2025 | Thu 05/08/2025 | 0% | Not Started
Erosion Control Seed | Fri 05/09/2025 | Fri 05/09/2025 | 0% | Not Started
Erect building batter boards and layout building | Fri 05/09/2025 | Mon 05/12/2025 | 0% | Not Started
Parking Lot Storm Collars | Fri 05/09/2025 | Tue 05/13/2025 | 0% | Not Started
Domestic Water, Fire, Sanitary & Electrical Stub Up Into Building | Tue 05/13/2025 | Fri 05/16/2025 | 0% | Not Started
Parking Lot Stone | Wed 05/14/2025 | Tue 05/20/2025 | 0% | Not Started
Excavate foundations | Mon 05/19/2025 | Fri 05/23/2025 | 0% | Not Started
Binder Course | Wed 05/21/2025 | Mon 05/26/2025 | 0% | Not Started
Cut & Stone Accel & Decel Lanes 181st St | Fri 05/23/2025 | Fri 05/23/2025 | 0% | Not Started
New Curbs Accel & Decel Lanes | Mon 05/26/2025 | Thu 05/29/2025 | 0% | Not Started
Form, set reinforcement, Anchor bolts and Pour spread foundations | Mon 05/26/2025 | Thu 05/29/2025 | 0% | Not Started
Dumpster Enclosure CMU | Tue 05/27/2025 | Mon 06/02/2025 | 0% | Not Started
Form & Pour Restaurant Side Grade Beam | Fri 05/30/2025 | Thu 06/05/2025 | 0% | Not Started
Erect steel columns, beams and joist - 1st and 2nd floors & Roof | Mon 06/02/2025 | Fri 06/27/2025 | 0% | Not Started
ROW Pavement | Wed 06/04/2025 | Wed 06/04/2025 | 0% | Not Started
Set Site Light Poles/pull wire & terminate | Thu 06/05/2025 | Tue 06/10/2025 | 0% | Not Started
Walk Path Asphalt & Stone | Thu 06/05/2025 | Wed 06/11/2025 | 0% | Not Started
Form & Pour Volleyball Grade Beam | Fri 06/06/2025 | Thu 06/12/2025 | 0% | Not Started
Steel Erection | Mon 06/09/2025 | Mon 08/11/2025 | 0% | Not Started
Detail openings level 2 | Mon 06/30/2025 | Wed 07/02/2025 | 0% | Not Started
Detail openings roof | Thu 07/03/2025 | Mon 07/07/2025 | 0% | Not Started
Metal Stairs | Thu 07/03/2025 | Wed 07/09/2025 | 0% | Not Started
Metal deck level 2 | Thu 07/03/2025 | Wed 07/09/2025 | 0% | Not Started
Set RTU Curbs | Tue 07/08/2025 | Tue 07/08/2025 | 0% | Not Started
Metal deck roof | Tue 07/08/2025 | Mon 07/21/2025 | 0% | Not Started
Metal Railings at Balconies & Opening in Building | Thu 07/10/2025 | Wed 07/16/2025 | 0% | Not Started
Under Slab Plumbing | Thu 07/10/2025 | Wed 07/23/2025 | 0% | Not Started
Under Slab Electrical | Thu 07/10/2025 | Wed 07/23/2025 | 0% | Not Started
Slab on Grade & Slab on Deck | Thu 07/10/2025 | Fri 09/05/2025 | 0% | Not Started
Building Exterior | Thu 07/17/2025 | Mon 10/20/2025 | 0% | Not Started
Set RTUs | Tue 07/22/2025 | Tue 07/22/2025 | 0% | Not Started
Pour back at columns Volleyball Court | Tue 07/22/2025 | Thu 07/24/2025 | 0% | Not Started
Exterior Metal Wall Panels | Tue 07/22/2025 | Mon 07/28/2025 | 0% | Not Started
Set Sleeves For Plumbing & Elect L2 SOD | Tue 07/22/2025 | Mon 07/28/2025 | 0% | Not Started
Solar Panel Installation | Wed 07/23/2025 | Tue 08/12/2025 | 0% | Not Started
Final Grade SOG | Thu 07/24/2025 | Tue 07/29/2025 | 0% | Not Started
Backfill Foundations | Fri 07/25/2025 | Tue 07/29/2025 | 0% | Not Started
Insulation Bats behind metal panels & Roof | Tue 07/29/2025 | Mon 08/04/2025 | 0% | Not Started
Sidewalks, stoops & Island Curbs | Tue 07/29/2025 | Mon 08/11/2025 | 0% | Not Started
Moisture Barrier SOG | Wed 07/30/2025 | Thu 08/07/2025 | 0% | Not Started
Interior Buildout VB Court | Thu 07/31/2025 | Mon 09/01/2025 | 0% | Not Started
Install OH Garage Doors | Tue 08/05/2025 | Thu 08/07/2025 | 0% | Not Started
Unit Heaters | Fri 08/08/2025 | Fri 08/08/2025 | 0% | Not Started
Slab Reinforcement SOG | Fri 08/08/2025 | Mon 08/11/2025 | 0% | Not Started
RI Electrical | Mon 08/11/2025 | Mon 08/11/2025 | 0% | Not Started
RI gas to heaters | Mon 08/11/2025 | Mon 08/11/2025 | 0% | Not Started
Install Topsoil | Tue 08/12/2025 | Thu 08/14/2025 | 0% | Not Started
Install Fans & Lights | Tue 08/12/2025 | Thu 08/14/2025 | 0% | Not Started
Pour SOG | Tue 08/12/2025 | Mon 08/18/2025 | 0% | Not Started
Hang & Finish Demising Wall | Tue 08/12/2025 | Mon 08/18/2025 | 0% | Not Started
Plants & Trees | Fri 08/15/2025 | Thu 08/21/2025 | 0% | Not Started
Prime & 1st Coat Demising Wall | Tue 08/19/2025 | Thu 08/21/2025 | 0% | Not Started
Slab Reinforcement L2 SOD | Tue 08/19/2025 | Fri 08/22/2025 | 0% | Not Started
CMU Exterior Walls | Tue 08/19/2025 | Mon 09/01/2025 | 0% | Not Started
Exterior Framing | Tue 08/19/2025 | Mon 09/01/2025 | 0% | Not Started
Interior Buildout level 1 | Thu 08/21/2025 | Wed 12/10/2025 | 0% | Not Started
Rock planter Beds | Fri 08/22/2025 | Fri 08/22/2025 | 0% | Not Started
Mulch planter Beds | Fri 08/22/2025 | Thu 08/28/2025 | 0% | Not Started
Volleyball Nets & Sand System | Fri 08/22/2025 | Thu 09/04/2025 | 0% | Not Started
Site Signage | Mon 08/25/2025 | Mon 08/25/2025 | 0% | Not Started
Pour L2 SOD | Mon 08/25/2025 | Mon 08/25/2025 | 0% | Not Started
Seed Grassed Areas | Tue 08/26/2025 | Thu 08/28/2025 | 0% | Not Started
Frame Walls & Ceilings | Tue 08/26/2025 | Mon 09/01/2025 | 0% | Not Started
Frame Walls & Ceilings | Tue 08/26/2025 | Mon 09/15/2025 | 0% | Not Started
Interior Buildout Level 2 | Tue 08/26/2025 | Thu 10/23/2025 | 0% | Not Started
Final Paving | Fri 08/29/2025 | Wed 09/03/2025 | 0% | Not Started
Fine Grade for Covered Patio SOG | Tue 09/02/2025 | Thu 09/04/2025 | 0% | Not Started
Exterior Sheathing | Tue 09/02/2025 | Mon 09/08/2025 | 0% | Not Started
RI Plumbing | Tue 09/02/2025 | Mon 09/08/2025 | 0% | Not Started
RI Electrical | Tue 09/02/2025 | Mon 09/15/2025 | 0% | Not Started
RI HVAC | Tue 09/02/2025 | Mon 09/15/2025 | 0% | Not Started
RI Sprinkler | Wed 09/03/2025 | Tue 09/09/2025 | 0% | Not Started
Form and Pour Patio SOG | Fri 09/05/2025 | Fri 09/05/2025 | 0% | Not Started
Framing Balcony & Patio Ceilings & Bulkheads | Mon 09/08/2025 | Fri 09/19/2025 | 0% | Not Started
Waterproofing | Tue 09/09/2025 | Thu 09/11/2025 | 0% | Not Started
Wood Cladding | Fri 09/12/2025 | Wed 09/17/2025 | 0% | Not Started
Doors & Windows | Fri 09/12/2025 | Thu 09/18/2025 | 0% | Not Started
Insulate Walls | Tue 09/16/2025 | Wed 09/17/2025 | 0% | Not Started
Install door frames and rough in call button box | Tue 09/16/2025 | Thu 09/18/2025 | 0% | Not Started
RI HVAC | Tue 09/16/2025 | Mon 09/29/2025 | 0% | Not Started
RI Fire Sprinkler | Tue 09/16/2025 | Mon 09/29/2025 | 0% | Not Started
RI Plumbing | Tue 09/16/2025 | Mon 10/06/2025 | 0% | Not Started
RI Electrical | Tue 09/16/2025 | Mon 10/06/2025 | 0% | Not Started
Elevators | Tue 09/16/2025 | Tue 11/18/2025 | 0% | Not Started
Install OH Garage Doors | Wed 09/17/2025 | Fri 09/19/2025 | 0% | Not Started
Hang & Finish Drywall | Thu 09/18/2025 | Fri 09/26/2025 | 0% | Not Started
EIFS | Fri 09/19/2025 | Thu 10/09/2025 | 0% | Not Started
Elect. Rough In Balcony & Patio Ceilings | Mon 09/22/2025 | Fri 10/03/2025 | 0% | Not Started
Striping & Pavement Markings | Thu 09/25/2025 | Thu 09/25/2025 | 0% | Not Started
Install HM Door Frames | Mon 09/29/2025 | Mon 09/29/2025 | 0% | Not Started
Install Air Curtains | Mon 09/29/2025 | Mon 09/29/2025 | 0% | Not Started
Install Roll Up Counter Doors | Mon 09/29/2025 | Tue 09/30/2025 | 0% | Not Started
Prime & 1st Coat Paint | Tue 09/30/2025 | Wed 10/01/2025 | 0% | Not Started
Polish & Seal Floors | Thu 10/02/2025 | Mon 10/06/2025 | 0% | Not Started
Bead Board Underside Balcony & Patio Ceilings | Mon 10/06/2025 | Fri 10/10/2025 | 0% | Not Started
Insulate Walls | Tue 10/07/2025 | Thu 10/09/2025 | 0% | Not Started
Install tile bathroom floors & walls | Tue 10/07/2025 | Thu 10/09/2025 | 0% | Not Started
Install Casework | Tue 10/07/2025 | Mon 10/13/2025 | 0% | Not Started
Install doors & hardware | Fri 10/10/2025 | Mon 10/13/2025 | 0% | Not Started
Trim out electrical | Fri 10/10/2025 | Thu 10/16/2025 | 0% | Not Started
Install Grills & Diffusers | Fri 10/10/2025 | Thu 10/16/2025 | 0% | Not Started
Hang & Finish Drywall | Fri 10/10/2025 | Thu 10/23/2025 | 0% | Not Started
Sealants Exterior Balcony & Patio | Mon 10/13/2025 | Tue 10/14/2025 | 0% | Not Started
Install Plumbing Fixtures | Tue 10/14/2025 | Wed 10/15/2025 | 0% | Not Started
Paint Beadboard Ceilings & Bulkheads | Wed 10/15/2025 | Fri 10/17/2025 | 0% | Not Started
Install Toilet Partitions & Specialties | Thu 10/16/2025 | Fri 10/17/2025 | 0% | Not Started
Final Paint | Mon 10/20/2025 | Wed 10/22/2025 | 0% | Not Started
Paint Metal Handrails | Mon 10/20/2025 | Thu 10/23/2025 | 0% | Not Started
Final Clean | Thu 10/23/2025 | Fri 10/24/2025 | 0% | Not Started
Install Roll Up Counter Doors | Fri 10/24/2025 | Fri 10/24/2025 | 0% | Not Started
Install HM Door Frames | Fri 10/24/2025 | Mon 10/27/2025 | 0% | Not Started
Set elevator Rails & equipment | Fri 10/24/2025 | Thu 10/30/2025 | 0% | Not Started
Vendor Build Out | Fri 10/24/2025 | Thu 12/18/2025 | 0% | Not Started
Restaurant & Bar | Fri 10/24/2025 | Thu 12/18/2025 | 0% | Not Started
Prime & 1st Coat Paint | Tue 10/28/2025 | Mon 11/03/2025 | 0% | Not Started
Build Cab | Fri 10/31/2025 | Thu 11/06/2025 | 0% | Not Started
Polish & Seal Floors | Tue 11/04/2025 | Mon 11/10/2025 | 0% | Not Started
Install Air Curtains | Thu 11/06/2025 | Mon 11/10/2025 | 0% | Not Started
Test and align doors and equipment | Fri 11/07/2025 | Thu 11/13/2025 | 0% | Not Started
Install tile bathroom floors & walls | Tue 11/11/2025 | Mon 11/17/2025 | 0% | Not Started
Install Casework | Tue 11/11/2025 | Mon 11/24/2025 | 0% | Not Started
Complete elevator inspection and certification | Fri 11/14/2025 | Tue 11/18/2025 | 0% | Not Started
Complete Final Inspections | Fri 11/14/2025 | Tue 12/16/2025 | 0% | Not Started
Install doors & hardware | Tue 11/18/2025 | Fri 11/21/2025 | 0% | Not Started
Trim out electrical | Tue 11/18/2025 | Mon 11/24/2025 | 0% | Not Started
Install Grills & Diffusers | Tue 11/18/2025 | Mon 11/24/2025 | 0% | Not Started
Install Plumbing Fixtures | Tue 11/25/2025 | Mon 12/01/2025 | 0% | Not Started
Install Toilet Partitions & Specialties | Tue 12/02/2025 | Mon 12/08/2025 | 0% | Not Started
Final Paint | Tue 12/09/2025 | Fri 12/12/2025 | 0% | Not Started
Final Clean | Mon 12/15/2025 | Wed 12/17/2025 | 0% | Not Started
Perform architect's inspection | Thu 12/18/2025 | Thu 12/18/2025 | 0% | Not Started
Perform local building agency inspection | Thu 12/18/2025 | Thu 12/18/2025 | 0% | Not Started
Perform Fire Marshal's inspection | Thu 12/18/2025 | Thu 12/18/2025 | 0% | Not Started
Obtain certificate of occupancy | Fri 12/19/2025 | Mon 12/22/2025 | 0% | Not Started
Complete punch list items from all inspections | Fri 12/19/2025 | Thu 01/01/2026 | 0% | Not Started
Issue final completion documents including warranties | Fri 01/02/2026 | Thu 01/15/2026 | 0% | Not Started
Issue final request for payment | Fri 01/16/2026 | Fri 01/16/2026 | 0% | Not Started
Milestones | Milestones | Milestones | Milestones | Milestones | Milestones | Milestones
Task Name | Date |  | Percent Complete | Status | Groups | Assigned To
Foundation Complete | Fri 06/13/2025 |  | 0% | Not Started
RI complete | Tue 10/07/2025 |  | 0% | Not Started
Dried In | Fri 10/10/2025 |  | 0% | Not Started
Turn Over Building | Tue 12/23/2025 |  | 0% | Not Started