## Sheet1
Source | Sub Job | Budget Code | Description | Scheduled Value | Work Completed (Previous) $ | Work Completed (Previous) % | Work Completed (This Period) $ | Work Completed (This Period) % | Total Completed and Stored | Balance To Finish | Retainage $ | Retainage % | Current Retainage $
PC-5296-0001 |  | 013120 - Vice President - Labor |  | 12189 | 9141.75 | 75% | 9141.75 | 75% | 9141.75 | 3047.25 | 0 | 0% | 0
PC-5296-0001 |  | 013126 - Pre-construction - Labor |  | 6581 | 3290.5 | 50% | 3290.5 | 50% | 3290.5 | 3290.5 | 0 | 0% | 0
PC-5296-0001 |  | 013127 - Sr. Project Manager - Labor |  | 7312 | 5484 | 75% | 5484 | 75% | 5484 | 1828 | 0 | 0% | 0
PC-5296-0001 |  | 013128 - Project Manager - Labor |  | 6094 | 4570.5 | 75% | 4570.5 | 75% | 4570.5 | 1523.5 | 0 | 0% | 0
PC-5296-0001 |  | 013245 - Office Supplies - Expense |  | 500 | 375 | 75% | 375 | 75% | 375 | 125 | 0 | 0% | 0
PC-5296-0001 |  | 014126 - Permit Requirements - Expense |  | 500 | 375 | 75% | 375 | 75% | 375 | 125 | 0 | 0% | 0
PC-5296-0001 |  | 015133 - Temporary Internet/Telecomm - Expense |  | 500 | 375 | 75% | 375 | 75% | 375 | 125 | 0 | 0% | 0
PC-5296-0001 |  | 016500 - Travel & Entertainment - Expense |  | 1000 | 750 | 75% | 750 | 75% | 750 | 250 | 0 | 0% | 0
PC-5296-0001 |  | 016505 - Marketing - Expense |  | 200 | 150 | 75% | 150 | 75% | 150 | 50 | 0 | 0% | 0
PC-5296-0001 |  | 034500 - Precast Architectural Concrete - Subcontract |  | 50000 | 42500 | 85% | 42500 | 85% | 42500 | 7500 | 0 | 0% | 0
PC-5296-0001 |  | 051200 - Structural Steel Framing - Subcontract |  | 30000 | 27000 | 90% | 27000 | 90% | 27000 | 3000 | 0 | 0% | 0
PC-5296-0001 |  | 522000 - Architectural Services - Subcontract |  | 210000 | 147000 | 70% | 147000 | 70% | 147000 | 63000 | 0 | 0% | 0
PC-5296-0001 |  | 550050 - Insurance - Expense |  | 4386 | 4386 | 100% | 4386 | 100% | 4386 | 0 | 0 | 0% | 0
PC-5296-0001 |  | 550500 - Contractor Fee - Expense |  | 36874 | 25811.8 | 70% | 25811.8 | 70% | 25811.8 | 11062.2 | 0 | 0% | 0
PCCO-5296-0002 |  | 522000 - Architectural Services - Subcontract | Architectural Redesign | 8824 | 6618 | 75% | 6618 | 75% | 6618 | 2206 | 0 | 0% | 0
PCCO-5296-0002 |  | 502000 - Site Engineering - Subcontract | Civil Redesign | 10000 | 7500 | 75% | 7500 | 75% | 7500 | 2500 | 0 | 0% | 0
PCCO-5296-0002 |  | 051200 - Structural Steel Framing - Subcontract | Structural Redesign | 25000 | 18750 | 75% | 18750 | 75% | 18750 | 6250 | 0 | 0% | 0
PCCO-5296-0002 |  | 550050 - Insurance - Expense | Insurance | 591.62 | 591.62 | 100% | 591.62 | 100% | 591.62 | 0 | 0 | 0% | 0
PCCO-5296-0002 |  | 550500 - Contractor Fee - Expense | Fee | 4439.37 | 3329.53 | 75% | 3329.53 | 75% | 3329.53 | 1109.84 | 0 | 0% | 0
|  |  | Grand Total | 414990.99 | 307998.7 | 77.11% | 307998.7 | 77.11% | 307998.7 | 106992.29 | 0 | 0% | 0