## RFI Log
Alleato Group
25-127 Ulta Beauty
RFI Log
Printed: 03/28/2026
Number | Title | Location | Response Due | Question | Accepted Responses | Requested By | Ball In Court | Assignee List | Distribution List | Groups | Status | Created On
06 | RFI - AC6 Relocation to H12 | AC6 | 03/23/2026 | Can we relocate AC6 south one column line from 11H to H12. The unit would sit on the West side of the girder. Please see attachment for reference. |  | Candon Rusin | Andre Audi | Andre Audi | Andre Audi |  | Open | 03/19/2026 07:28 PM
05 | RFI – RTU Curb Support Angles: Welding |  | 02/25/2026 | Please confirm if the proposed repair below is acceptable, or advise if you would like us to proceed with an alternate repair/detail. We are proposing the following repair approach to address the gap at the roof decking: Install a 3/8" plate slid into the gap as a backing/shim plate. Stitch weld the plate to the supporting members 2" welds @ 12" o.c. Straighten any bent deck as needed and puddle weld the deck back down to the support. |  | Candon Rusin | Andre Audi | Andre Audi | Andre Audi | 05 Metals | Closed | 02/25/2026 12:52 PM
04 | RFI – AC-5 Relocation at Grid C-20: Structural Approval + Welding Details | AC-5 Column C-20 | 02/17/2026 | Please confirm the proposed relocation of AC-5 to the opposite side of Column C-20 is structurally acceptable. If acceptable, please provide the required structural/welding details for the relocation. |  | Candon Rusin | Andre Audi | Andre Audi | Andre Audi |  | Closed | 02/12/2026 08:24 PM
03 | RFI – AC-6 Relocation at Grid H-11: Structural Approval + Welding Details | AC6 Column H-11 | 02/16/2026 | Please confirm the proposed relocation of AC-6 to the opposite side of Column H-11 is structurally acceptable. If acceptable, please provide the required structural/welding details for the relocation. |  | Candon Rusin | Andre Audi | Andre Audi | Andre Audi | 05 Metals | Closed | 02/12/2026 08:14 PM
02 | HVLS Relocation Verification | Ulta Beauty DC | 02/05/2026 | Existing HVLS fan locations conflict with existing ceiling utilities and associated supports. See attached “HVLS Location Conflicts” plan for proposed new fan locations. Please review and confirm that the new proposed HVLS relocations are acceptable. |  | Candon Rusin | Andre Audi | Andre Audi | Andre Audi |  | Closed | 02/03/2026 08:36 PM
01 | RFI – AC-1 Relocation at Grid B-15: Structural Approval + Welding Details | RTU AC-1 on Column B-15 | 01/30/2026 | Please confirm the proposed relocation of AC-1 to the opposite side of Column B-15 is structurally acceptable. If acceptable, please provide the required structural/welding details for the relocation. |  | Candon Rusin | Andre Audi | Andre Audi | Andre Audi | 05 Metals | Closed | 01/26/2026 04:35 PM