## Budget
Budget Code | Original Budget | Budget Modifications | Contract Change Orders | Revised Budget | Actual Amount | Pending Budget Changes | Projected Budget | Direct Costs | Commitments | Commitment Change Orders | Committed Costs | Projected Costs | Committed Invoiced Amount | Pending Cost Changes | Forecast To Complete | Estimated Cost at Completion | Project Over/Under
013120 - Vice President - Labor | 0 | 40000 | 0 | 40000 | 39248.25 | 0 | 40000 | 39248.25 | 0 | 0 | 39248.25 | 39248.25 | 0 | 0 | 751.75 | 40000 | 0
013126 - Pre-construction - Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
013128 - Project Manager - Labor | 45552 | 10000 | 0 | 55552 | 52961.85 | 0 | 55552 | 52961.85 | 0 | 0 | 52961.85 | 52961.85 | 0 | 0 | 2590.15 | 55552 | 0
013129 - Assistant Project Manager (APM) - Labor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
013144 - Superintendent - Labor | 40500 | 0 | 0 | 40500 | 21101.21 | 0 | 40500 | 21101.21 | 0 | 0 | 21101.21 | 21101.21 | 0 | 0 | 19398.79 | 40500 | 0
013245 - Office Supplies - Expense | 450 | 3060.42 | 0 | 3510.42 | 3510.42 | 0 | 3510.42 | 3510.42 | 0 | 0 | 3510.42 | 3510.42 | 0 | 0 | 0 | 3510.42 | 0
013247 - Printing & Copying - Expense | 2250 | 0 | 0 | 2250 | 312.54 | 0 | 2250 | 312.54 | 0 | 0 | 312.54 | 312.54 | 0 | 0 | 1937.46 | 2250 | 0
014126 - Permit Requirements - Expense | 15000 | 0 | 0 | 15000 | 5598.18 | 0 | 15000 | 5598.18 | 0 | 0 | 5598.18 | 5598.18 | 0 | 0 | 9401.82 | 15000 | 0
014523 - Testing and Inspections - Expense | 3500 | 1000 | 0 | 4500 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 4500 | 0
015133 - Temporary Internet/Telecomm - Expense | 0 | 1553.46 | 0 | 1553.46 | 1193.46 | 0 | 1553.46 | 1193.46 | 0 | 0 | 1193.46 | 1193.46 | 0 | 0 | 360 | 1553.46 | 0
015133 - Temporary Internet/Telecomm - Labor | 0 | 350 | 0 | 350 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 350 | 0
015213 - Field Offices - Expense | 0 | 635 | 0 | 635 | 634.25 | 0 | 635 | 634.25 | 0 | 0 | 634.25 | 634.25 | 0 | 0 | 0.75 | 635 | 0
015214 - Temporary Storage - Expense | 0 | 1500 | 0 | 1500 | 241 | 0 | 1500 | 241 | 0 | 0 | 241 | 241 | 0 | 0 | 1259 | 1500 | 0
016113 - Software Licensing - Expense | 1500 | 0 | 0 | 1500 | 917.35 | 0 | 1500 | 917.35 | 0 | 0 | 917.35 | 917.35 | 0 | 0 | 582.65 | 1500 | 0
016500 - Travel & Entertainment - Expense | 36000 | 0 | 0 | 36000 | 28164.3 | 0 | 36000 | 28164.3 | 0 | 0 | 28164.3 | 28164.3 | 0 | 0 | 7835.7 | 36000 | 0
016500 - Travel & Entertainment - Labor | 0 | 748 | 0 | 748 | 0 | 0 | 748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 748 | 748 | 0
016502 - Truck Allowance - Expense | 3300 | 0 | 0 | 3300 | 854.7 | 0 | 3300 | 854.7 | 0 | 0 | 854.7 | 854.7 | 0 | 0 | 2445.3 | 3300 | 0
016503 - Truck Fuel - Expense | 1200 | 1000 | 0 | 2200 | 1727.37 | 0 | 2200 | 1727.37 | 0 | 0 | 1727.37 | 1727.37 | 0 | 0 | 472.63 | 2200 | 0
017333 - Misc Small Tools - Expense | 0 | 428.43 | 0 | 428.43 | 422.65 | 0 | 428.43 | 422.65 | 0 | 0 | 422.65 | 422.65 | 0 | 0 | 5.78 | 428.43 | 0
017336 - Equipment Rental - Expense | 3750 | 0 | 0 | 3750 | 0 | 0 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3750 | 3750 | 0
017413 - Progress Cleaning - Expense | 3250 | 0 | 0 | 3250 | 0 | 0 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3250 | 3250 | 0
017419 - Dumpsters - Expense | 4500 | 0 | 0 | 4500 | 1530 | 0 | 4500 | 1530 | 0 | 0 | 1530 | 1530 | 0 | 0 | 2970 | 4500 | 0
017423 - Final Cleaning - Expense | 2500 | 0 | 0 | 2500 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 0
017425 - General Labor - Subcontract | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
051100 - Miscellaneous Metals - Subcontract | 0 | 7292 | 0 | 7292 | 0 | 0 | 7292 | 0 | 7292 | 0 | 7292 | 7292 | 0 | 0 | 0 | 7292 | 0
051200 - Structural Steel Framing - Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
051200 - Structural Steel Framing - Subcontract | 227500 | 250000 | 0 | 477500 | 0 | 0 | 477500 | 0 | 454638 | 10297.49 | 464935.49 | 464935.49 | 0 | 0 | 12564.51 | 477500 | 0
075400 - Thermoplastic Roofing (TPO) - Subcontract | 72000 | -40000 | 0 | 32000 | 0 | 0 | 32000 | 0 | 21435 | 0 | 21435 | 21435 | 0 | 0 | 10565 | 32000 | 0
211313 - Wet-Pipe Sprinkler System - Subcontract | 23500 | 0 | 0 | 23500 | 0 | 0 | 23500 | 0 | 7684 | 7916 | 15600 | 15600 | 0 | 0 | 7900 | 23500 | 0
221116 - Domestic Water Piping - Subcontract | 92500 | -46821.29 | 0 | 45678.71 | 0 | 0 | 45678.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45678.71 | 45678.71 | 0
233439 - HVLS Fans - Subcontract | 100000 | -100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
237000 - Central HVAC Equipment - Expense | 0 | 72605.38 | 0 | 72605.38 | 70621.44 | 0 | 72605.38 | 70621.44 | 0 | 0 | 70621.44 | 70621.44 | 0 | 0 | 1983.94 | 72605.38 | 0
237000 - Central HVAC Equipment - Subcontract | 1332000 | -289784.59 | 0 | 1042215.41 | 0 | 0 | 1042215.41 | 0 | 1020000 | 22215.41 | 1042215.41 | 1042215.41 | 0 | 0 | 0 | 1042215.41 | 0
261000 - Med-Volt Elect Distribution - Subcontract | 800000 | -400000 | 0 | 400000 | 272695 | 0 | 400000 | 0 | 337735 | 13271.38 | 351006.38 | 351006.38 | 272695 | 0 | 48993.62 | 400000 | 0
274000 - Fire Alarm & Life Safety Syst - Subcontract | 63000 | 0 | 0 | 63000 | 26750 | 0 | 63000 | 0 | 53500 | 0 | 53500 | 53500 | 26750 | 0 | 9500 | 63000 | 0
284000 - Life Safety - Expense | 0 | 150 | 0 | 150 | 150 | 0 | 150 | 150 | 0 | 0 | 150 | 150 | 0 | 0 | 0 | 150 | 0
505000 - Structural Engineering - Expense | 0 | 13805.65 | 0 | 13805.65 | 13805.65 | 0 | 13805.65 | 0 | 13805.65 | 0 | 13805.65 | 13805.65 | 13805.65 | 0 | 0 | 13805.65 | 0
505000 - Structural Engineering - Subcontract | 20000 | -13805.65 | 0 | 6194.35 | 2500 | 0 | 6194.35 | 0 | 0 | 3500 | 3500 | 3500 | 2500 | 0 | 2694.35 | 6194.35 | 0
505500 - HVAC Engineering - Subcontract | 41000 | 0 | 0 | 41000 | 0 | 0 | 41000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41000 | 41000 | 0
523000 - Design Development - Subcontract | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
550050 - Insurance - Expense | 36685 | 4971.03 | 0 | 41656.03 | 41656.03 | 0 | 41656.03 | 41656.03 | 0 | 0 | 41656.03 | 41656.03 | 0 | 0 | 0 | 41656.03 | 0
550099 - Unallocated Costs - Expense | 0 | 481312.16 | 0 | 481312.16 | 0 | 0 | 481312.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 481312.16 | 481312.16 | 0
550500 - Contractor Fee - Expense | 297144 | 0 | 0 | 297144 | 0 | 0 | 297144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 297144 | 297144 | 0
Grand Total: | 3268581 | -5.8208e-11 | 0 | 3268581 | 586595.65 | 0 | 3268581 | 270845 | 1916089.65 | 57200.28 | 2244134.93 | 2244134.93 | 315750.65 | 0 | 1024446.07 | 3268581 | 0