## Sheet1
Report Type: Change Request
Project: 25-127 Ulta Beauty
Title Number | Contract | Scope | Status | Cost | Revenue | Markup | Tax | Total | Over/Under
CR-5347-0001 Special Inspections for structural | PC-5347-0001 | Internal | Draft | 4075 | 0 | 0 | 0 | 0 | -4075
CR-5347-0003 KascoFab Equipment 1 week Rental | PC-5347-0001 | Internal | Approved | 10297 | 0 | 0 | 0 | 0 | -10297
CR-5347-0002 Conflict with RTU and existing utilities | PC-5347-0001 | Internal | Draft | 73386 | 0 | 0 | 0 | 0 | -73386
|  |  |  | 87758.21 | 0 | 0 | 0 | 0 | -87758.21