## Sheet1
Report Type: Submittal
Project: 25-127 Ulta Beauty
Submittal Number | Title | Due Date | Item Types | Trades | Submitter | Status | Ball In Court
3 | HVLS Fans | 11/21/2025 | Drawings, Specification Sheets | 26 Electrical | Mark Worthington | Closed | Approvers
4 | Roofing Submittal | 12/26/2025 | Specification Sheets | 07 Thermal and Moisture Protection | Ryan Ward | Closed | Approvers
5 | Mod Distribution Fans | 12/22/2025 | Specification Sheets | 23 HVAC | Keith Dunn | Closed | Approvers
8 | RTU and Curb Submittal | 01/19/2026 | Specification Sheets | 07 Thermal and Moisture Protection | Ryan Ward | Closed | Approvers
9 | HVAC Duct Sock | 01/17/2026 | Specification Sheets | 23 HVAC | Keith Dunn | Closed | Approvers
6 | Carlisle Curb Flashing | 12/29/2025 | Specification Sheets | 07 Thermal and Moisture Protection | Ryan Ward | Approved | Nobody
7 | MOD Diffusers | 01/16/2026 | Specification Sheets | 23 HVAC | Keith Dunn | Approved | Nobody
10 | Electrical 600A Panels | 01/29/2026 | Specification Sheets | 26 Electrical | Mark Worthington | Approved | Nobody
11 | Electrical Wire and Connectors | 01/29/2026 | Specification Sheets | 26 Electrical | Mark Worthington | Approved | Nobody