## Budget
Budget Code | Original Budget | Budget Modifications | Contract Change Orders | Revised Budget | Actual Amount | Pending Budget Changes | Projected Budget | Direct Costs | Commitments | Commitment Change Orders | Committed Costs | Projected Costs | Committed Invoiced Amount | Pending Cost Changes | Forecast To Complete | Estimated Cost at Completion | Project Over/Under
013120 - Vice President - Expense | 0 | 3539.46 | 0 | 3539.46 | 666.66 | 0 | 3539.46 | 666.66 | 0 | 0 | 666.66 | 666.66 | 0 | 0 | 2872.8 | 3539.46 | 0
013120 - Vice President - Labor | 0 | 42793.77 | 0 | 42793.77 | 42793.77 | 0 | 42793.77 | 42793.77 | 0 | 0 | 42793.77 | 42793.77 | 0 | 0 | 0 | 42793.77 | 0
013126 - Pre-construction - Expense | 25960 | -25960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
013126 - Pre-construction - Subcontract | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
013127 - Sr. Project Manager - Labor | 0 | 25771.75 | 0 | 25771.75 | 25771.75 | 0 | 25771.75 | 25771.75 | 0 | 0 | 25771.75 | 25771.75 | 0 | 0 | 0 | 25771.75 | 0
013128 - Project Manager - Labor | 101250 | -20679.04 | 0 | 80570.96 | 81135.33 | 0 | 80570.96 | 81135.33 | 0 | 0 | 81135.33 | 81135.33 | 0 | 0 | 0 | 81135.33 | -564.37
013130 - Project Engineer - Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
013130 - Project Engineer - Labor | 97200 | -14341.49 | 0 | 82858.51 | 79736.6 | 0 | 82858.51 | 79736.6 | 0 | 0 | 79736.6 | 79736.6 | 0 | 0 | 3121.91 | 82858.51 | 0
013132 - Intern - Labor | 0 | 12817.23 | 0 | 12817.23 | 12817.23 | 0 | 12817.23 | 12817.23 | 0 | 0 | 12817.23 | 12817.23 | 0 | 0 | 0 | 12817.23 | 0
013144 - Superintendent - Labor | 135000 | 0 | 0 | 135000 | 118863.25 | 0 | 135000 | 118863.25 | 0 | 0 | 118863.25 | 118863.25 | 0 | 0 | 16136.75 | 135000 | 0
013145 - Assistant Superintendent - Labor | 0 | 0 | 0 | 0 | 4220.42 | 0 | 0 | 4220.42 | 0 | 0 | 4220.42 | 4220.42 | 0 | 0 | 0 | 4220.42 | -4220.42
013245 - Office Supplies - Expense | 1500 | 3396.39 | 0 | 4896.39 | 6691.49 | 0 | 4896.39 | 6691.49 | 0 | 0 | 6691.49 | 6691.49 | 0 | 0 | 0 | 6691.49 | -1795.1
013247 - Printing & Copying - Expense | 1500 | 2017.22 | 0 | 3517.22 | 3517.22 | 0 | 3517.22 | 3517.22 | 0 | 0 | 3517.22 | 3517.22 | 0 | 0 | 0 | 3517.22 | 0
013249 - Postage & Courier - Expense | 0 | 12.65 | 0 | 12.65 | 12.65 | 0 | 12.65 | 12.65 | 0 | 0 | 12.65 | 12.65 | 0 | 0 | 0 | 12.65 | 0
014126 - Permit Requirements - Expense | 0 | -2375.1 | 43711.08 | 41335.98 | 41807.55 | 0 | 41335.98 | 41807.55 | 0 | 0 | 41807.55 | 41807.55 | 0 | 0 | 0 | 41807.55 | -471.57
014523 - Testing and Inspections - Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
014523 - Testing and Inspections - Subcontract | 0 | 10060 | 0 | 10060 | 8551 | 0 | 10060 | 0 | 8551 | 0 | 8551 | 8551 | 8551 | 0 | 1509 | 10060 | 0
015113 - Temporary Electric - Expense | 10000 | 0 | 0 | 10000 | 3232.77 | 0 | 10000 | 3232.77 | 0 | 0 | 3232.77 | 3232.77 | 0 | 0 | 6767.23 | 10000 | 0
015129 - Temporary Gas - Expense | 0 | 14.13 | 0 | 14.13 | 14.13 | 0 | 14.13 | 14.13 | 0 | 0 | 14.13 | 14.13 | 0 | 0 | 0 | 14.13 | 0
015133 - Temporary Internet/Telecomm - Expense | 0 | 2000 | 0 | 2000 | 1166.99 | 0 | 2000 | 1166.99 | 0 | 0 | 1166.99 | 1166.99 | 0 | 0 | 833.01 | 2000 | 0
015133 - Temporary Internet/Telecomm - Labor | 0 | 0 | 0 | 0 | 210 | 0 | 0 | 210 | 0 | 0 | 210 | 210 | 0 | 0 | 0 | 210 | -210
015213 - Field Offices - Expense | 9500 | 4760 | 0 | 14260 | 14119.95 | 0 | 14260 | 14119.95 | 0 | 0 | 14119.95 | 14119.95 | 0 | 0 | 140.05 | 14260 | 0
015214 - Temporary Storage - Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
015216 - First Aid / Safety Supplies - Expense | 750 | 449.36 | 0 | 1199.36 | 1199.36 | 0 | 1199.36 | 1199.36 | 0 | 0 | 1199.36 | 1199.36 | 0 | 0 | 0 | 1199.36 | 0
015217 - Safety Inspections - Expense | 6000 | -272.72 | 0 | 5727.28 | 0 | 0 | 5727.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5727.28 | 5727.28 | 0
015219 - Temporary Toilets - Expense | 14000 | 0 | 0 | 14000 | 5750 | 0 | 14000 | 5750 | 0 | 0 | 5750 | 5750 | 0 | 0 | 8250 | 14000 | 0
015623 - Temporary Barricades - Expense | 0 | 149.65 | 0 | 149.65 | 149.65 | 0 | 149.65 | 149.65 | 0 | 0 | 149.65 | 149.65 | 0 | 0 | 0 | 149.65 | 0
015626 - Tempoary Fencing - Expense | 5000 | 20000 | 1200.62 | 26200.62 | 21593.61 | 0 | 26200.62 | 21593.61 | 0 | 0 | 21593.61 | 21593.61 | 0 | 0 | 4607.01 | 26200.62 | 0
015639 - Temp Tree & Plant Protection - Expense | 0 | 2352.12 | 1447.88 | 3800 | 3800 | 0 | 3800 | 3800 | 0 | 0 | 3800 | 3800 | 0 | 0 | 0 | 3800 | 0
015813 - Temporary Project Signage - Expense | 0 | 13201.49 | 0 | 13201.49 | 11122.9 | 0 | 13201.49 | 11122.9 | 0 | 0 | 11122.9 | 11122.9 | 0 | 0 | 2078.59 | 13201.49 | 0
016113 - Software Licensing - Expense | 0 | 7497.35 | 0 | 7497.35 | 3116.71 | 0 | 7497.35 | 3116.71 | 0 | 0 | 3116.71 | 3116.71 | 0 | 0 | 4380.64 | 7497.35 | 0
016500 - Travel & Entertainment - Expense | 12000 | 1000 | 0 | 13000 | 9758.2 | 0 | 13000 | 9758.2 | 0 | 0 | 9758.2 | 9758.2 | 0 | 0 | 3241.8 | 13000 | 0
016502 - Truck Allowance - Expense | 12000 | -10000 | 0 | 2000 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 0
016503 - Truck Fuel - Expense | 8000 | -5014.13 | 0 | 2985.87 | 2073.42 | 0 | 2985.87 | 2073.42 | 0 | 0 | 2073.42 | 2073.42 | 0 | 0 | 912.45 | 2985.87 | 0
016505 - Marketing - Expense | 0 | 2119.89 | 0 | 2119.89 | 2119.89 | 0 | 2119.89 | 2119.89 | 0 | 0 | 2119.89 | 2119.89 | 0 | 0 | 0 | 2119.89 | 0
017333 - Misc Small Tools - Expense | 5000 | 0 | 0 | 5000 | 2752.46 | 0 | 5000 | 2752.46 | 0 | 0 | 2752.46 | 2752.46 | 0 | 0 | 2247.54 | 5000 | 0
017333 - Misc Small Tools - Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
017336 - Equipment Rental - Expense | 7500 | 0 | 0 | 7500 | 3684.27 | 0 | 7500 | 3684.27 | 1425 | 0 | 5109.27 | 5109.27 | 0 | 0 | 2390.73 | 7500 | 0
017413 - Progress Cleaning - Expense | 6500 | 12000 | 0 | 18500 | 19962.67 | 0 | 18500 | 19962.67 | 0 | 0 | 19962.67 | 19962.67 | 0 | 0 | 0 | 19962.67 | -1462.67
017413 - Progress Cleaning - Subcontract | 0 | 2500 | 0 | 2500 | 0 | 0 | 2500 | 0 | 2500 | 0 | 2500 | 2500 | 0 | 0 | 0 | 2500 | 0
017416 - Site Maintenance - Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
017419 - Dumpsters - Expense | 16250 | 0 | 0 | 16250 | 12428.41 | 0 | 16250 | 12428.41 | 0 | 0 | 12428.41 | 12428.41 | 0 | 0 | 3821.59 | 16250 | 0
017841 - Project Final Photos - Expense | 0 | 350 | 0 | 350 | 350 | 0 | 350 | 350 | 0 | 0 | 350 | 350 | 0 | 0 | 0 | 350 | 0
020150 - Maintenance & Site Remediation - Subcontract | 37000 | -17500 | 2784.38 | 22284.38 | 14092.5 | 0 | 22284.38 | 0 | 19500 | 1650 | 21150 | 21150 | 14092.5 | 0 | 1134.38 | 22284.38 | 0
026500 - Undergrnd Storage Tank Removal - Expense | 0 | 1140 | 0 | 1140 | 1140 | 0 | 1140 | 1140 | 0 | 0 | 1140 | 1140 | 0 | 0 | 0 | 1140 | 0
032000 - Foundations - Subcontract | 652762 | -3122.7 | -70308.89 | 579330.41 | 631037.98 | 0 | 579330.41 | 0 | 482091 | 152946.98 | 635037.98 | 635037.98 | 631037.98 | 0 | 0 | 635037.98 | -55707.57
032500 - Concrete Subbase - Subcontract | 38350 | -38350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
042200 - Concrete Unit Masonry-Block - Subcontract | 127500 | -30433.35 | -8436.65 | 88630 | 78630 | 0 | 88630 | 0 | 76600 | 12030 | 88630 | 88630 | 78630 | 0 | 0 | 88630 | 0
051100 - Miscellaneous Metals - Expense | 0 | -2853.13 | 8353.13 | 5500 | 5500 | 0 | 5500 | 0 | 5500 | 0 | 5500 | 5500 | 5500 | 0 | 0 | 5500 | 0
051200 - Structural Steel Framing - Subcontract | 2213500 | 173417.65 | -612103.07 | 1774814.58 | 1658209.25 | 0 | 1774814.58 | 0 | 1624500 | 151719.58 | 1776219.58 | 1776219.58 | 1658209.25 | 0 | 0 | 1776219.58 | -1405
055100 - Metal Stairs - Subcontract | 130500 | -35511.49 | 67730.49 | 162719 | 162719 | 0 | 162719 | 0 | 125681 | 37038 | 162719 | 162719 | 162719 | 0 | 0 | 162719 | 0
055823 - Formed Metal Guards - Subcontract | 0 | 9500 | 0 | 9500 | 0 | 0 | 9500 | 0 | 9500 | 0 | 9500 | 9500 | 0 | 0 | 0 | 9500 | 0
055900 - Metal Specialties - Material | 10400 | -10400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
055900 - Metal Specialties - Subcontract | 0 | 9700 | 0 | 9700 | 9700 | 0 | 9700 | 0 | 9700 | 0 | 9700 | 9700 | 9700 | 0 | 0 | 9700 | 0
057000 - Decorative Metal - Subcontract | 18200 | -8250 | 0 | 9950 | 9950 | 0 | 9950 | 0 | 15410 | -5460 | 9950 | 9950 | 9950 | 0 | 0 | 9950 | 0
061100 - Wood Framing - Expense | 0 | 478.33 | 0 | 478.33 | 478.33 | 0 | 478.33 | 478.33 | 0 | 0 | 478.33 | 478.33 | 0 | 0 | 0 | 478.33 | 0
062000 - Finish Carpentry - Expense | 0 | 7217.47 | 0 | 7217.47 | 7217.47 | 0 | 7217.47 | 7217.47 | 0 | 0 | 7217.47 | 7217.47 | 0 | 0 | 0 | 7217.47 | 0
062000 - Finish Carpentry - Material | 0 | 45000 | 0 | 45000 | 43881.97 | 0 | 45000 | 0 | 49302.14 | 0 | 49302.14 | 49302.14 | 43881.97 | 0 | 0 | 49302.14 | -4302.14
062000 - Finish Carpentry - Subcontract | 30000 | -45035.63 | 15035.63 | 0 | 0 | 0 | 0 | 0 | 3556.88 | 0 | 3556.88 | 3556.88 | 0 | 0 | 0 | 3556.88 | -3556.88
072100 - Thermal Insulation - Subcontract | 0 | 2100 | 0 | 2100 | 0 | 0 | 2100 | 0 | 2100 | 0 | 2100 | 2100 | 0 | 0 | 0 | 2100 | 0
072400 - Ext Ins & Finish Syst (EFIS) - Subcontract | 65998 | -1726.78 | 0 | 64271.22 | 35072.22 | 0 | 64271.22 | 273.22 | 58998 | 5000 | 64271.22 | 64271.22 | 34799 | 0 | 0 | 64271.22 | 0
078400 - Firestopping - Expense | 15000 | -15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
078400 - Firestopping - Subcontract | 0 | -3599.63 | 18599.63 | 15000 | 4048 | 0 | 15000 | 0 | 15000 | 7000 | 22000 | 22000 | 4048 | 0 | 0 | 22000 | -7000
081113 - Hollow Metal Door and Frames - Material | 0 | 55033.92 | 3065.51 | 58099.43 | 58099.43 | 0 | 58099.43 | 0 | 55547.01 | 2552.42 | 58099.43 | 58099.43 | 58099.43 | 0 | 0 | 58099.43 | 0
081113 - Hollow Metal Door and Frames - Subcontract | 48409 | -34116.72 | -6712.87 | 7579.41 | 5474.27 | 0 | 7579.41 | 0 | 0 | 10227.66 | 10227.66 | 10227.66 | 5474.27 | 0 | 0 | 10227.66 | -2648.25
081216 - Aluminum Frames - Subcontract | 10500 | -10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
083300 - Coiling Doors and Grilles - Subcontract | 32000 | -32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
083600 - Overhead Doors - Subcontract | 124000 | 3638 | -44550 | 83088 | 83088 | 0 | 83088 | 0 | 85620 | -2532 | 83088 | 83088 | 83088 | 0 | 0 | 83088 | 0
084300 - Storefronts - Material | 0 | -1915 | 0 | -1915 | 0 | 0 | -1915 | 0 | 0 | -1915 | -1915 | -1915 | 0 | 0 | 0 | -1915 | 0
084300 - Storefronts - Subcontract | 100500 | 8534.11 | 46150.89 | 155185 | 135509 | 0 | 155185 | 0 | 100755 | 54430 | 155185 | 155185 | 135509 | 0 | 0 | 155185 | 0
087900 - Hardware Accessories - Subcontract | 5800 | -5800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
090500 - Demolition for Finishes - Subcontract | 12000 | -1975 | 0 | 10025 | 0 | 0 | 10025 | 0 | 10025 | 0 | 10025 | 10025 | 0 | 0 | 0 | 10025 | 0
092216 - Non-Structural Metal Framing - Labor | 0 | 1320 | 0 | 1320 | 1320 | 0 | 1320 | 0 | 0 | 1320 | 1320 | 1320 | 1320 | 0 | 0 | 1320 | 0
092216 - Non-Structural Metal Framing - Subcontract | 568750 | 32528.3 | -93156.61 | 508121.69 | 445167.62 | 0 | 508121.69 | 0 | 428986 | 88391 | 517377 | 517377 | 445167.62 | 0 | 0 | 517377 | -9255.31
093000 - Ceramic Tile - Labor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
093000 - Ceramic Tile - Subcontract | 20000 | 10426.92 | 96800.9 | 127227.82 | 875 | 0 | 127227.82 | 0 | 20000 | 90725 | 110725 | 110725 | 875 | 0 | 16502.82 | 127227.82 | 0
096200 - Specialty Flooring - Subcontract | 72000 | -60668.75 | 5568.75 | 16900 | 10100 | 0 | 16900 | 0 | 14100 | 4600 | 16900 | 16900 | 10100 | 0 | 0 | 16900 | 0
097216 - Wall Coverings - Subcontract | 40000 | -66636.53 | 29486.53 | 2850 | 2850 | 0 | 2850 | 0 | 2850 | 0 | 2850 | 2850 | 2850 | 0 | 0 | 2850 | 0
099113 - Exterior Painting - Subcontract | 30000 | -3000 | 0 | 27000 | 26393.31 | 0 | 27000 | 0 | 27000 | -606.69 | 26393.31 | 26393.31 | 26393.31 | 0 | 606.69 | 27000 | 0
099123 - Interior Painting - Subcontract | 30000 | 46071.49 | 22720.51 | 98792 | 84431.55 | 0 | 98792 | 0 | 60000 | 38792 | 98792 | 98792 | 84431.55 | 0 | 0 | 98792 | 0
101400 - Signage - Subcontract | 5000 | -5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102813 - Toilet Accessories - Expense | 0 | 29757 | 0 | 29757 | 208.64 | 0 | 29757 | 208.64 | 29757 | 0 | 29965.64 | 29965.64 | 0 | 0 | 0 | 29965.64 | -208.64
102813 - Toilet Accessories - Subcontract | 25800 | -26384.38 | 3501.34 | 2916.96 | 0 | 0 | 2916.96 | 0 | 0 | 2552.68 | 2552.68 | 2552.68 | 0 | 0 | 364.28 | 2916.96 | 0
104116 - Knox Box - Expense | 2500 | -1274.85 | 0 | 1225.15 | 1225.15 | 0 | 1225.15 | 1225.15 | 0 | 0 | 1225.15 | 1225.15 | 0 | 0 | 0 | 1225.15 | 0
104416 - Fire Extinguishers - Material | 3000 | -3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104416 - Fire Extinguishers - Subcontract | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267.35 | 0 | 267.35 | 267.35 | 0 | 0 | 0 | 267.35 | -267.35
123000 - Casework - Subcontract | 107500 | -80424.85 | 28543.62 | 55618.77 | 14461 | 0 | 55618.77 | 0 | 28922 | 27814.87 | 56736.87 | 56736.87 | 14461 | 0 | 0 | 56736.87 | -1118.1
123500 - Specialty Casework - Subcontract | 0 | -21496.36 | 116122.36 | 94626 | 42500 | 0 | 94626 | 0 | 103354 | -4370 | 98984 | 98984 | 42500 | 0 | 0 | 98984 | -4358
142000 - Elevators - Subcontract | 93500 | 0 | 0 | 93500 | 58360 | 0 | 93500 | 0 | 93500 | 0 | 93500 | 93500 | 58360 | 0 | 0 | 93500 | 0
211313 - Wet-Pipe Sprinkler System - Subcontract | 149000 | 31220.62 | -46220.62 | 134000 | 0 | 0 | 134000 | 0 | 134000 | 0 | 134000 | 134000 | 0 | 0 | 0 | 134000 | 0
211316 - Dry-Pipe Sprinkler Systems - Subcontract | 30000 | -30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
221000 - Plumbing Piping - Subcontract | 234100 | 5357.05 | 117755.37 | 357212.42 | 334066.67 | 0 | 357212.42 | 0 | 217000 | 139352.42 | 357212.42 | 357212.42 | 334066.67 | 0 | 0 | 357212.42 | 0
233000 - HVAC Air Distribution - Expense | 21000 | -21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233000 - HVAC Air Distribution - Subcontract | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233439 - HVLS Fans - Expense | 0 | 36320.29 | 0 | 36320.29 | 36320.29 | 0 | 36320.29 | 16179.89 | 20140.4 | 0 | 36320.29 | 36320.29 | 20140.4 | 0 | 0 | 36320.29 | 0
237000 - Central HVAC Equipment - Subcontract | 264000 | 32541.25 | 1838.75 | 298380 | 298380 | 0 | 298380 | 0 | 412000 | -107990 | 304010 | 304010 | 298380 | 0 | 0 | 304010 | -5630
261000 - Med-Volt Elect Distribution - Subcontract | 713500 | 322100.55 | 113633.62 | 1149234.17 | 967339.42 | 0 | 1149234.17 | 0 | 738500 | 411863.18 | 1147757.22 | 1147757.22 | 967339.42 | 0 | 1476.95 | 1149234.17 | 0
265500 - Special Purpose Lighting - Subcontract | 200000 | -200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
265600 - Exterior Lighting - Subcontract | 75000 | -75284.38 | 2784.38 | 2500 | 2500 | 0 | 2500 | 0 | 0 | 2500 | 2500 | 2500 | 2500 | 0 | 0 | 2500 | 0
312213 - Rough Grading - Subcontract | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
312316 - Excavation - Subcontract | 731018 | 75239.19 | -60093.3 | 746163.89 | 688827.19 | 0 | 746163.89 | 0 | 567222.13 | 184661.76 | 746163.89 | 746163.89 | 688827.19 | 0 | 0 | 746163.89 | 0
316200 - Driven Piles - Subcontract | 62500 | -1200 | 0 | 61300 | 61300 | 0 | 61300 | 0 | 61300 | 0 | 61300 | 61300 | 61300 | 0 | 0 | 61300 | 0
321216 - Asphalt Paving - Subcontract | 316088 | -49868.17 | 23228.37 | 289448.2 | 229587.33 | 0 | 289448.2 | 0 | 327461.25 | -38013.05 | 289448.2 | 289448.2 | 229587.33 | 0 | 0 | 289448.2 | 0
329000 - Planting - Subcontract | 76199 | -3699 | 0 | 72500 | 13937.68 | 0 | 72500 | 0 | 72500 | 0 | 72500 | 72500 | 13937.68 | 0 | 0 | 72500 | 0
330504 - Utility Relocations - Expense | 0 | -2310.01 | 32670.19 | 30360.18 | 30360.18 | 0 | 30360.18 | 30360.18 | 0 | 0 | 30360.18 | 30360.18 | 0 | 0 | 0 | 30360.18 | 0
330504 - Utility Relocations - Subcontract | 20000 | -20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
501250 - Geotechnical Report - Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
504200 - Traffic Engineering Design - Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
522000 - Architectural Services - Subcontract | 0 | -3898.13 | 3898.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
523000 - Design Development - Expense | 0 | 110746.57 | 8032 | 118778.57 | 118778.57 | 0 | 118778.57 | 118778.57 | 0 | 0 | 118778.57 | 118778.57 | 0 | 0 | 0 | 118778.57 | 0
523000 - Design Development - Subcontract | 142250 | -96329.8 | 0 | 45920.2 | 45920.2 | 0 | 45920.2 | 45920.2 | 0 | 0 | 45920.2 | 45920.2 | 0 | 0 | 0 | 45920.2 | 0
524000 - Construction Documents - Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
524000 - Construction Documents - Subcontract | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
550050 - Insurance - Expense | 82251 | 7270.58 | 0 | 89521.58 | 89521.58 | 0 | 89521.58 | 89521.58 | 0 | 0 | 89521.58 | 89521.58 | 0 | 0 | 0 | 89521.58 | 0
550099 - Unallocated Costs - Expense | 182000 | -136146.17 | -9135.87 | 36717.96 | 0 | 0 | 36717.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36717.96 | 36717.96 | 0
550100 - Contingency - Expense | 131601 | 0 | -131601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
550500 - Contractor Fee - Expense | 679389 | 58891.54 | 0 | 738280.54 | 0 | 0 | 738280.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 738280.54 | 738280.54 | 0
Grand Total: | 9255275 | -3.638e-11 | -267654.82 | 8987620.18 | 7093769.11 | 0 | 8987620.18 | 847942.54 | 6120722.16 | 1266280.81 | 8225679.55 | 8225679.55 | 6245826.57 | 0 | 866122 | 9091801.55 | -104181.37